Youth Pullet-Rearing Enterprises

Evidence-based business plan developed from the BENEFIT-REALISE HwU Cluster pilot work plan 'Small-scale poultry enterprises to promote dissemination of improved breeds and enhance youth employment'

Two model enterprises, each owned by 10 young women, in two kebeles of two woredas (names not stated in the source)

| Item | Detail |
| --- | --- |
| Document status | Draft for validation - for management, lenders, investors and development partners |
| Preparation date | 23 October 2026 |
| Research cut-off date | 23 October 2026 (web sources accessed 22-23 Oct 2026) |
| Source proposal | BENEFIT REALISE Project HwU Cluster Work plan (project period stated as 2018-2020) - reference R1 |
| Currency and prices | Ethiopian birr (ETB), nominal. Original figures are as written; new projections are at Oct 2026 planning prices |
| Companion files | Poultry_Financial_Model.xlsx (live formulas, scenario switch); Vermicompost business plan and model (new component) |

How to read this plan - evidence labels used throughout [O] Original proposal information, reproduced without correction. [V] Independently verified current information, with a dated reference (R-numbers, Annex 8). [A] New planning assumption made for this plan - must be validated. [G] Gap, contradiction or item requiring clarification. Nothing in this plan should be read as evidence that houses, groups, sales, loans or partnerships already exist. The source is a pilot work plan; no implementation report was provided.

# 1. Diagnostic assessment of the original proposal

The source document is a one-year activity work plan for a grant-funded university pilot. It is not a business proposal. It sets out a sound development idea: young women raise improved-breed chicks past the high-mortality brooding stage and sell pullets to farmers. However, it gives none of the commercial information a lender or investor needs: chick numbers, prices, sales volumes, customers, cost per bird or arrangements after the grant ends.

| Dimension | Assessment | Rating |
| --- | --- | --- |
| Concept and relevance | Clear rationale [O]: low egg output of local free-range chickens; improved breeds recommended by HU research (Dawud et al., 2018 - citation not verified [G]). Youth and women focus aligned with PSNP livelihood pathways. | Strong |
| Business model | Revenue source identified (sale of ~2-month pullets) [O], but no volumes, prices or buyers. Who pays - PSNP households, NGOs or government - is not analysed. | Weak |
| Technical design | Key elements present (brooders, feeders, vaccine, feed, electricity criterion, training) [O]. Missing: batch size, floor area, vaccination schedule, biosecurity, mortality target, sexing of chicks, breed suitability. | Partial |
| Budget | Line items sum exactly to ETB 300,000 [O]. 38.7% is capacity building and M&E; no working capital beyond one month of feed; no allocation between the two enterprises [G]. Prices are 2018-2020 vintage and now far out of date. | Weak for enterprise use |
| Sustainability | Relies on 'linkage' to suppliers, credit and markets [O] with no confirmed partner, credit amount or offtake. | Weak |
| Schedule | Sep.-Aug. activity list with blank timing and responsibility cells; no year stated [G]. | Incomplete |
| Internal consistency | Several contradictions (house funding, feed production, implementing clusters) - see Annex 3. | Needs clarification |
| Verdict | Supports a pilot, not full commercial investment. This plan converts it into a costed pilot-to-enterprise pathway with decision gates. | PILOT |

# 2. Business plan

## A. Executive summary

Opportunity. Smallholders in southern Ethiopia keep low-producing local chickens [O]. Improved and dual-purpose birds need heated, vaccinated brooding for the first weeks, which households cannot easily provide. A local enterprise that buys day-old chicks (DOC), rears them for about two months [O] and sells vaccinated pullets fills that gap. Development agencies currently tender for 45-day pullets [V: R14, R15], which shows institutional demand. The willingness of PSNP households to pay cash has not been tested [G].

Enterprise. Two youth enterprises, each of 10 young women [O], organised as legal entities through the woreda cooperative office [O]. Each is to run in a woreda-built poultry house in a kebele with electricity [O]. The project supplies inputs for the first batch [O]. All facilities, groups and partnerships are proposed. None is verified as established.

Production plan [A]. Each enterprise places 500 DOC per batch, every three months (4 batches a year at full operation). At 10% mortality it sells 450 pullets per batch, or 1,800 a year from PY2. All quantities are new assumptions; the source states no chick numbers.

Investment and funding. Original grant budget: ETB 300,000 for both enterprises [O]. The plan re-costs one enterprise at Oct 2026 prices [A]: ETB 295,000 of fixed assets (of which ETB 250,000 is the woreda's in-kind house and ETB 15,000 the project's equipment grant). ETB 30,000 is cash-funded. Working capital is financed by ETB 20,000 member equity and a ETB 100,000 working-capital loan, which is not yet identified [A].

Financial outlook (base case, one enterprise) [A]. Sales of ETB 607,500 in PY1 rise to ETB 1,274,551 in PY5 (nominal, 12% a year escalation). EBITDA excluding grants is ETB 102,338 in PY1 and ETB 155,064 in PY2. Net profit excluding grants is ETB 50,297 in PY1 and ETB 102,334 in PY2. The lowest month-end cash in PY1 is ETB 17,000, and the loan is repaid in PY2 (DSCR 2.06 and 1.98). Full-cost NPV at 25% is ETB 101,103 (IRR 36%; payback 2.9 years).

Margins are thin and sensitive. Contribution is ETB 156 per pullet sold (35%). Break-even is about 1,176 pullets a year, a price of ETB 396 per pullet, or survival of 79%. A price of ETB 380 instead of 450, or 20% mortality instead of 10%, each turns the five-year NPV negative. The combined downside case has a negative contribution per bird and would need ETB 1,667,675 of unplanned funding over five years.

Livelihood effect. In PY2 the base case pays ETB 120,960 in duty allowances and earns ETB 102,334 net profit. That is about ETB 22,329 per member per year (~ETB 1,861 a month): a useful supplementary income, not a full livelihood for ten members.

Major risks. Disease (Newcastle disease remains a threat even in vaccinated flocks [V: R18]); feed and DOC price inflation (CPI 15.3% in July 2026 [V: R2]); unreliable DOC supply and unsexed chicks; buyers' ability to pay; dependence on one-off NGO orders; and electricity cuts during brooding.

Recommendation: PILOT, then decide. The evidence supports one or two pilot batches per enterprise using the original grant inputs. Full commercial operation and any borrowing should wait until these gates are met: (1) written price quotations for DOC, feed and vaccines; (2) pre-orders with deposits for at least 60% of a batch at ETB 396 or more per pullet; (3) at least 85% survival to sale in the pilot batch; (4) confirmation of the woreda house, a veterinary service plan and the group's legal registration. Environmental and social benefits do not, on their own, make the enterprise viable.

## B. Enterprise description and objectives

| Attribute | Original proposal [O] | Status / comment |
| --- | --- | --- |
| Name | BENEFIT REALISE Project HwU Cluster - 'Small-scale poultry enterprises ...' | No trading name given. Each group should register its own name [G]. |
| Ownership | Two groups of 10 unemployed young women, organised as legal entities | Legal form not specified; woreda cooperative office involvement suggests a cooperative or youth association [G]. |
| Development stage | Pilot within a three-year (2018-2020) grant project | Planned, grant-supported start-up. Implementation not verified. Project period has elapsed [G]. |
| Location | Two kebeles in two different woredas; kebeles with electricity; 'Southern Ethiopia' context | Woredas, kebeles and region not named [G]. Hawassa is now the seat of the Sidama Region; the implementing clusters (Hawassa, Arsi, Woldiya) span several regions. |
| Assets | House by woreda; DOC, brooder boxes, feeders, one month of feed from project; corrugated iron and nails for house | None confirmed as delivered. |
| Lead persons | Responsible Body: Gurmessa Umeta/ Asfaw Tafesse; Implementing clusters: Hawassa, Arsi, Woldiya University; Lead Cluster: Mekele University | Roles inside the enterprises not defined [G]. |

### Strategic objectives

Original objectives [O], reproduced verbatim:

To establish small-scale poultry enterprises as a means of job creation for unemployed youth,

To promote small-scale poultry production models that will serve as distribution centers of improved poultry breeds to farmers,

To improve farmer's access to improved chicken breeds

Measurable targets proposed by this plan [A] (per enterprise, from PY2):

| Target | Base value | Basis |
| --- | --- | --- |
| Batches placed per year | 4 | 3-month cycle (about 2 months rearing [O] + 1 month sale, cleaning, rest) |
| DOC placed per batch | 500 | Fits a ~30 m2 rearing floor at 15-20 birds/m2 to 8 weeks [A] |
| Survival to sale | >= 90% (minimum 85%) | Accounting break-even survival 79% |
| Pullets sold per year | 1,800 | 500 x 4 x 90% |
| Average realised price (PY1 prices) | >= ETB 450 (floor ETB 396) | Break-even price at planned volume |
| Repeat or referred customers | >= 40% of buyers by PY2 | Customer register |
| Cash collected within 30 days | >= 95% of invoiced sales | Receivables control |
| Paid member duty-days per month | >= 36 (3 members x 12 days) | Allowance budget ETB 9,000/month [A] |

### Location suitability checklist [A]

The woredas and kebeles are not named [G], so location suitability cannot yet be assessed. The site-selection activity [O] should score candidate kebeles on the criteria below:

| Criterion | Minimum requirement | Why it matters |
| --- | --- | --- |
| Electricity [O] | Grid connection at the house plus a backup heat source (charcoal/kerosene brooder) | Chicks die quickly if brooding heat fails |
| Water | Safe water within 200 m; ~5 m3 per batch [A] | Drinking water and cleaning |
| Road access | All-weather road to a DOC pick-up point; 4-6 hour maximum chick transport [A] | Chick stress and mortality in transit |
| Biosecurity distance | House away from markets, live-bird trading and other flocks; fenced | Newcastle disease and HPAI risk |
| Buyers | At least 3-5 kebeles of PSNP and other households within 15 km; DA and vet offices nearby | Sales and extension |
| Feed supply | Feed mill or agro-dealer reachable within one day | Feed is ~51% of variable cost |
| Land tenure | Written woreda/kebele allocation of the plot for at least 5 years | Asset security; lender requirement |
| Security | Free movement for staff and inputs (check with woreda administration) | Business continuity |

## C. Market and competition

No market research, price data or customer commitments are included in the original proposal [G]. The segments below are possible customer groups to be tested, not established demand.

| Segment | Need and purchasing behaviour (to verify) | Affordability / payment | Evidence status |
| --- | --- | --- | --- |
| PSNP and other smallholder households [O target] | 5-10 pullets at a time; prefer dual-purpose birds that scavenge and brood; buy when grain and feed are available after harvest | Low cash income; may need instalments or VSLA/credit linkage | Assumed [A]; preference checklist planned [O] |
| NGO and government livelihood programmes | Large orders of 45-60-day vaccinated pullets, often Sasso or Bovans/Lohmann; tenders specify breed, age, vaccination, VAT | Pay on invoice after delivery; 30-60 days | Active tenders Aug 2026 [V: R14, R15]; no award prices found |
| Woreda livestock/agriculture offices | Breed-dissemination packages; demonstrations | Budget-cycle dependent | Plausible [A] |
| Small commercial egg producers (peri-urban) | Layer pullets (Lohmann Brown) in batches of 50-300 | Cash; price-sensitive | Plausible [A] |
| Traders and village agents | Resale to farmers; margin-driven | Cash on collection | Plausible [A]; competes with EthioChicken agent network [V: R16] |

### Price comparison (consistent units)

| Item | Unit | Price (ETB) | Date / place | Source | Comment |
| --- | --- | --- | --- | --- | --- |
| Pullet (original proposal) | per bird | not stated | 2018-2020 | R1 [O] | Gap [G] |
| Pullets | per bird | 100-120 | Feb 2020, national | R13 | Price at proposal date |
| 2-month vaccinated Bovans Brown | per bird | 710 | undated listing, Addis Ababa | R12 | Single asking price |
| Pullet - plan base / downside / upside | per bird | 450 / 380 / 520 | Oct 2026 planning | [A] | Rural farm-gate; to test |
| Day-old chick | per chick | ~50 | pre-2024 press | R11 | Historical |
| Day-old chick - plan base | per chick | 100 | Oct 2026 planning | [A] | Get hatchery quotes |
| Layer feed | per 100 kg | 2,695 (1,800-4,000) | 2022, Arsi/East Shewa | R10 | Pre-devaluation |
| Layer mash (vendor web page) | per 100 kg | 8,800 | 2026, unverified | web vendor | Weak evidence |
| Starter/grower feed - plan base | per 100 kg | 8,000 | Oct 2026 planning | [A] | Get feed-mill quotes |

Since the July 2024 float the birr has lost more than half its value. It traded at about 160-164 per USD in Sep-Oct 2026 [V: R6, R7]. Feed (maize, soybean meal, imported premixes) and imported genetics are therefore far more expensive than in the original budget. Reliable commercial feed price series are lacking [V: R35]. Local quotations are essential.

### Accessible demand estimate (transparent, to be validated)

| Step | Low | Base | High | Basis |
| --- | --- | --- | --- | --- |
| Kebeles served within ~15 km | 3 | 4 | 5 | [A] |
| Households per kebele | 800 | 1,000 | 1,200 | [A] - obtain kebele data |
| Share of households buying improved pullets per year | 5% | 8% | 12% | [A] - interview test |
| Pullets per purchase | 4 | 5 | 8 | [A] |
| Household demand (pullets/yr) | 480 | 1,600 | 5,760 | Product of the above |
| Institutional orders (pullets/yr) | 0 | 500 | 1,500 | [A] - tender-dependent |
| Total accessible demand | 480 | 2,100 | 7,260 |  |
| Planned sales per enterprise (PY2) | 1,800 | 1,800 | 1,800 | Model |
| Coverage of plan by demand | 27% | 117% | 403% |  |

In the low case household demand covers only about a quarter of planned output, so the plan depends on institutional orders. Before PY1 starts, run (a) 60 structured buyer interviews across three kebeles, (b) a pre-order campaign with 20-30% deposits, and (c) registration with the NGOs that run tenders. Free or heavily subsidised bird distribution by other programmes in the same kebeles would undercut paid sales and must be mapped [G].

### Competition and alternatives

Private hatcheries and agent networks (e.g. EthioChicken, Sasso and Bovans [V: R16]): reliable genetics and distribution; may sell 45-day birds directly.

Public multiplication centres (e.g. Debre Zeit ARC, named in the original as DOC source [O]; ACGG brooding facilities [V: R17]).

Other youth/MSE brooding units promoted by woreda job-creation offices.

Local chickens bought in village markets: cheaper and adapted, but low-producing - the problem the project addresses [O].

Advantages of this enterprise: proximity (lower transport stress), vaccinated birds, advice at sale, and links to PSNP and woreda structures [O].

## D. Products and value proposition

| Product | Specification [A unless marked] | Intended customer | Notes |
| --- | --- | --- | --- |
| Koekoek pullets [O breed] | Female, ~8 weeks [O 'about two months'], vaccinated (Marek's at hatchery; NCD, Gumboro, fowl pox per vet schedule), dewormed, healthy | Households, NGOs | Dual-purpose; better suited to semi-scavenging. Sexed DOC or a cockerel sales plan needed [G] |
| Lohmann Brown pullets [O breed; spelled 'Lohman' in source] | As above | Small egg producers | Commercial hybrid layer: needs balanced feed and housing to perform; weak fit for free-range PSNP households; cannot be bred on-farm [A] |
| Optional: alternative breeds (Sasso, Bovans) | As above | Tender-led orders | Only if buyers specify; not in the original proposal |
| By-product: used litter | ~2 t per batch [A] | Own vermicompost unit / farmers | See separate vermicompost plan |
| Service: buyer advice | Short guidance at sale (housing, feeding, vaccination boosters) | All buyers | Supports survival and repeat sales |

Value proposition: 'Vaccinated, past-the-brooding-risk improved pullets, delivered close to home with advice.' The plan makes no claims about egg yields or income gains for buyers. The breed-preference and productivity checklist in the original monitoring plan [O] should produce that evidence.

## E. Technical feasibility and operations

| Element | Plan [A unless marked] |
| --- | --- |
| House | Woreda-built [O]; project corrugated iron and nails [O]. ~35 m2 total: ~30 m2 rearing floor, 5 m2 store; ventilated sides with curtains; concrete or compacted floor; footbath; fenced. |
| Brooding | Brooder boxes [O] with electric heat and charcoal backup; 32-35 C at chick level in week 1, reduced ~3 C per week; ~50 chicks/m2 under the brooder in week 1, expanding to 15-20 birds/m2 by week 8. |
| Equipment | Brooders, feeders and drinkers [O]; thermometer, weighing scale, spray pump, PPE. Re-costed at ETB 45,000 per enterprise against ETB 15,000 original per-group allocation. |
| Feed | Starter (to ~6 weeks) then grower; ~1.7 kg per bird placed to 8 weeks incl. wastage [A, verify with breed guides R36]. Project funds first month only [O]. 'Poultry feed production' [O] is not planned until a separate feasibility study is done [G]. |
| Health | Vaccination schedule from woreda veterinarian and NVI products; strict all-in/all-out; 2-3 week cleaning and rest between batches; dead-bird log; no visitors in brooding week. |
| Chick sourcing | Debre Zeit ARC [O] or private hatchery [V: R16]; confirm sexing, Marek's vaccination, delivery time and minimum order. Book 2 months ahead. |
| Records | Batch card (placement date, number, source, deaths/day, feed issued, vaccinations, weights at weeks 4 and 8, sales, buyer). |
| Labour | 3 members on rotating daily duty (paid allowance [A]); management committee meets weekly. |
| Waste and safety | Litter removed after each batch to pre-composting (vermicompost unit) or farmers; deep-burial pit for carcasses; masks and gloves for cleaning; handwashing; report sudden mass deaths to the woreda vet immediately (HPAI/NCD). |

### Material flow per batch and per year (base) [A]

| Flow | Per batch | Per year (4 batches) | Calculation |
| --- | --- | --- | --- |
| DOC placed | 500 | 2,000 | Assumption |
| Mortality (10%) | 50 | 200 | 500 x 10% |
| Pullets sold | 450 | 1,800 | 500 - 50 |
| Feed used | 850 kg | 3,400 kg | 500 x 1.7 kg |
| Water (drinking + cleaning) | ~5 m3 | ~20 m3 | ~0.15 L/bird/day x 500 x 60 days + cleaning |
| Used litter (droppings + sawdust) | ~2 t | ~8 t | Estimate; weigh at first clean-out |
| Carcasses to dispose | ~50 | ~200 | Burial pit / incineration |

Capacity reconciliation. Floor space (500 birds at 15-20/m2 = 25-33 m2), labour (3 duty members) and the 3-month cycle are consistent. The binding constraints are working capital (ETB 80-130k per batch at Oct 2026 prices), DOC delivery reliability and demand. Production should not be scaled above demand secured by pre-orders.

## F. Marketing and sales strategy

| Element | Approach [A] |
| --- | --- |
| Pricing | Cost-plus floor: price at least the variable cost per pullet sold (ETB 294) plus fixed-cost recovery, i.e. above the ETB 396 break-even. List price ETB 450 (PY1). Review at every batch against feed and DOC costs. |
| Pre-orders | Open an order book 6 weeks before placement; 20-30% deposit; confirm 60% of a batch before ordering DOC. |
| Institutional sales | Register (TIN, trade licence) and keep a supplier profile; respond to NGO tenders; obtain health certificates from the woreda vet for each delivery. |
| Distribution | Collection at the house (default); delivery in ventilated crates to kebele centres on market days; transport charged per trip. |
| Promotion | DA and PSNP office briefings [O linkage]; demonstration households; radio or church/mosque announcements; leaflets in local language. |
| Retention | Follow-up visit or phone call at 4 weeks after sale; booster-vaccination reminders; referral discount. |
| Payment and collection | Cash or mobile money (telebirr/M-Pesa) on collection for households; written purchase orders and invoices for institutions; credit limit and 30-day terms. |
| Budget | Selling and transport ETB 4,000 per batch (PY1) in the model; promotion within administration line. |

| Sales KPI | Target | Responsible |
| --- | --- | --- |
| Pre-orders confirmed before DOC order | >= 60% of batch | Sales lead |
| Pullets sold within 2 weeks of reaching 8 weeks | >= 95% | Sales lead |
| Average price realised vs list | >= 95% | Treasurer |
| Receivables older than 30 days | <= 5% of sales | Treasurer |
| Customer complaints (dead/ill birds within 7 days) | <= 2% of birds | Production lead |

## G. Management and governance

Organisation [A]: general assembly of all 10 members; elected management committee (chair, secretary, treasurer); production lead and sales lead appointed from members; 3 members on rotating daily duty. External support: HU community service department (training, exchange visits) [O]; woreda cooperative office (legal entity) [O]; woreda PSNP office (member selection) [O]; woreda veterinarian and DA [A].

| Function | Controls |
| --- | --- |
| Training [O] | Poultry management, team work, book keeping and accounting (original ETB 28,000 + exchange visits ETB 20,000 for both groups). Add: biosecurity, vaccination, customer service, tender documents [A]. |
| Procurement | Three written quotations for purchases above ETB 10,000; committee approval minuted; goods received note. |
| Inventory | Feed and drug stock cards; bird register reconciled weekly (placed - dead - sold = on hand). |
| Finance | Bank account in the group's name with two of three signatories; cash book and receipt books; monthly bank reconciliation; no personal loans from group funds. |
| Reporting | Monthly report (production, sales, cash, problems) to members, woreda cooperative office and project; annual audit as required by cooperative law. |
| Profit use | Policy set by general assembly: reserve (e.g. 30%) for next-batch working capital before any distribution [A]. |

Owner labour. The model pays ETB 9,000 a month in duty allowances (3 members x ETB 3,000) as a cash cost. Other members' time (~4 days a month each) is unpaid. It is valued at ETB 7,000 a month (ETB 250/day [A]) in a memo line, which gives an economic profit of ETB (12,703) in PY1 and ETB 8,254 in PY2. Once all time is valued, returns to the group's labour are close to the local daily wage assumption.

## H. Financial plan and funding strategy

### H1. Original budget baseline (preserved exactly) [O]

| Activites (original wording and spelling) | Planned budget in Birr | Share |
| --- | --- | --- |
| Procurument of industial inpout for Poultery house construction/renovation | 40,000 | 13.3% |
| Purchase of poultery feed/ | 70,000 | 23.3% |
| Purchase of vaccsine / medicine | 12,000 | 4.0% |
| Purchase of equipments /brooder box, watering, feeder , saw dust etc | 30,000 | 10.0% |
| Provision of trainings ( Group formation, book keeping, Poltery production management | 28,000 | 9.3% |
| Conducting of exchange visites | 20,000 | 6.7% |
| Purchased of day old chikens | 32,000 | 10.7% |
| Monitoring and Evaluation | 68,000 | 22.7% |
| Total (as stated) | 300,000 | 100.0% |

Analytical findings (do not replace the source figures):

The eight lines sum to ETB 300,000, so the stated total reconciles.

Direct production inputs and assets (house inputs, feed, vaccine, equipment, DOC) = ETB 184,000 (61.3%). Capacity building and M&E = ETB 116,000 (38.7%). M&E alone is 22.7%.

No allocation between the two enterprises is given [G]. This plan assumes an equal split for analysis only: ETB 92,000 of direct inputs per enterprise.

Chick numbers and unit prices are not stated, so the scale implied by ETB 32,000 for DOC cannot be determined [G]. At the Oct 2026 planning price of ETB 100 per chick [A] it would buy 320 chicks (160 per group). At ETB 80/kg [A], ETB 70,000 of feed buys ~875 kg, about one 500-bird batch in total.

The budget has no working capital after the first month of feed, no contingency, and no line for the woreda's house contribution [G].

### H2. Re-costed start-up requirement per enterprise at Oct 2026 prices [A]

| Item | ETB | Funding | Comment |
| --- | --- | --- | --- |
| Poultry house (full value; woreda in-kind incl. project iron sheets/nails) | 250,000 | In-kind (woreda + project) | Valuation assumption; woreda to confirm |
| Equipment | 45,000 | 15,000 project grant + 30,000 cash | Original ETB 30,000 for two groups |
| Legal registration (pre-operating) | 3,000 | Cash |  |
| First-batch inputs (DOC, feed, vaccine) | 33,700 | 57,000 project in-kind + balance cash | Original lines split equally |
| Working capital to first collections (fixed costs, 2nd-month feed, energy) | covered by loan | Loan ETB 100,000 + equity ETB 20,000 | Lowest PY1 month-end cash ETB 17,000 |

Funding structure (base) [A]: in-kind house ETB 250,000; project equipment grant ETB 15,000; project first-batch inputs ETB 57,000 (non-cash grant income in PY1); member equity ETB 20,000; working-capital loan ETB 100,000 at 22% a year, 2 months interest-only then 18 equal monthly instalments. The NBE policy rate is 16% after the July 2026 increase, and bank credit-growth caps have been removed [V: R3, R4]. No lender has been approached [G]. Possible sources to explore: Sidama Bank (formerly Sidama MFI) [V: R33], other regional MFIs, youth revolving funds, and the DBE women/youth agricultural SME credit line announced in June 2026 [V: R32].

### H3. Unit economics and break-even (PY1 prices, base) [A]

| Measure | Value (ETB) |
| --- | --- |
| Variable cost per bird placed | 265 |
| Variable cost per pullet sold (after 10% mortality) | 294 |
| of which feed / day-old chick | 151 / 111 |
| Selling price per pullet | 450 |
| Contribution per pullet sold | 156 (35%) |
| Fixed cash costs (PY2, at PY1 prices) + depreciation + interest | 182,910 |
| Accounting break-even volume | 1,176 pullets/yr (2.6 batches) |
| Break-even revenue | 529,132 |
| Cash break-even incl. loan principal (PY2) | 1,375 pullets/yr |
| Break-even price at 1,800 pullets/yr | 396 |
| Break-even survival at ETB 450 and 2,000 DOC/yr | 79.2% |
| Margin of safety (volume) | 35% |

### H4. Five-year summary (base, one enterprise, nominal ETB) [A]

| Item | PY1 | PY2 | PY3 | PY4 | PY5 |
| --- | --- | --- | --- | --- | --- |
| Pullets sold | 1,350 | 1,800 | 1,800 | 1,800 | 1,800 |
| Sales revenue | 607,500 | 907,200 | 1,016,064 | 1,137,992 | 1,274,551 |
| EBITDA excluding grants | 102,338 | 155,064 | 173,672 | 194,512 | 217,854 |
| Net profit | 107,297 | 102,334 | 125,705 | 144,461 | 165,468 |
| Net profit excluding grant income | 50,297 | 102,334 | 125,705 | 144,461 | 165,468 |
| Net cash from operations | 63,719 | 126,062 | 151,415 | 168,352 | 188,147 |
| Closing cash | 118,661 | 179,781 | 331,196 | 499,549 | 687,695 |
| Loan outstanding | 64,942 | - | - | - | - |
| DSCR | 2.06 | 1.98 | n/a | n/a | n/a |

Full statements, PY1 monthly cash flow and assumptions are in Annex 4. Profit is not cash: PY1 net profit includes ETB 57,000 of non-cash grant income, and receivables tie up 40% of each batch's sales for a month. Grants are shown below the operating result, so the enterprise's own earning power (EBITDA excluding grants) is visible.

### H5. Investment appraisal [A]

| View | NPV @ 25% | IRR | Payback (years) |
| --- | --- | --- | --- |
| A. Full economic cost (in-kind house and grants counted as investment) | 101,103 | 36% | 2.9 |
| B. Enterprise view (only cash-funded capex counted) | 411,703 | very high - not meaningful | 0.4 |

Discount rate rationale: nominal 25% = NBE policy rate 16% plus a premium for start-up, livestock-disease and price risk. It is consistent with CPI inflation of 15.3% (July 2026) [V: R2]. View B shows that viability for the members depends heavily on the woreda and project contributions.

## I. Scenarios and risk management

| Indicator (one enterprise) | Base | Downside | Upside |
| --- | --- | --- | --- |
| Key assumptions | Price 450; mortality 10%; DOC 100; feed 80/kg; 4 batches/yr | Price 380; mortality 20%; DOC 120; feed 95/kg; 3 batches/yr; 1-month delay; 40% cash sales; costs +15%/yr | Price 520; mortality 7%; DOC 90; feed 75/kg |
| Sales PY1-5 | 4,943,306 | 2,523,170 | 5,902,674 |
| Net profit PY1-5 | 645,265 | (1,707,657) | 1,846,705 |
| Net profit PY2 | 102,334 | (286,435) | 323,131 |
| Additional funding required PY1-5 | - | 1,667,675 | - |
| NPV @ 25% (full cost) | 101,103 | (995,966) | 740,695 |
| Contribution per pullet (PY1 prices) | 156 | (32) | 268 |

### Single-factor sensitivity (each factor moved to its downside value, all else base)

| Factor moved to downside | Net profit PY1-5 | Extra funding needed | NPV @ 25% |
| --- | --- | --- | --- |
| Base case | 645,265 | 0 | 101,103 |
| Mortality to sale (~8 weeks) | 150,934 | 37,152 | (150,237) |
| Selling price of ~8-week pullet | (54,470) | 102,942 | (253,471) |
| Starter/grower feed price | 365,144 | - | (44,112) |
| Day-old chick price | 425,562 | - | (12,791) |
| Months between batch placements | 245,035 | 2,146 | (66,793) |
| Share of sales collected in month of sale | 645,265 | - | 78,954 |
| Month of first day-old-chick (DOC) placement | 511,387 | - | 36,392 |
| Selling and transport | 601,324 | - | 78,324 |
| Annual selling-price escalation | 290,791 | - | (50,309) |

Selling price, survival and feed/DOC prices drive results. Timing and payment terms matter much less. Price discipline at every batch and biosecurity are therefore the critical management tasks.

### Risk register

| Risk | Likelihood | Impact | Warning indicator | Mitigation | Responsible |
| --- | --- | --- | --- | --- | --- |
| Disease outbreak (NCD, Gumboro, HPAI) | M | H | Daily deaths > 0.5% of flock; drop in feed intake | Vaccination per vet schedule; all-in/all-out; footbath; visitor control; emergency vet contact | Production lead / woreda vet |
| Pullet price below break-even | M | H | Pre-orders below 60% or offered price < ETB 396 | Pre-order deposits; institutional tenders; adjust batch size; stop placement if gate missed | Sales lead |
| Feed and DOC cost inflation | H | M-H | Quoted feed > ETB 90/kg or DOC > ETB 115 | Price review each batch; bulk feed purchase with deposit; pass-through in contracts | Treasurer |
| DOC supply delay or unsexed/poor chicks | M | M | Hatchery cannot confirm date 6 weeks ahead | Two approved suppliers; written order terms; reject weak chicks on arrival | Chair |
| Electricity interruption during brooding | M | H | Outage > 2 hours | Charcoal/kerosene brooder backup; insulated brooder guard | Duty members |
| Delayed payment by institutions | M | M | Receivables > 30 days | Written POs; deposits; credit limits | Treasurer |
| Group conflict / member drop-out | M | M | Absences from duty roster; disputes | By-laws, duty roster, transparent accounts, mediation by coop office | Chair / coop office |
| Free bird distribution by other programmes | M | M | Announced NGO distributions in catchment | Coordinate with woreda; sell to those programmes | Chair |
| Theft and predators | L-M | M | Unexplained losses | Fencing, locks, night guard rota | Chair |
| Security / access restrictions | Varies by region | H | Road closures | Hold 1 month of feed stock; flexible batch timing | Chair / woreda |

## J. Implementation and monitoring

### J1. Original activity schedule (preserved) [O]

| Activities | Who is responsible? | Sep. | Oct. | Nov. | Dec. | Jan | Feb | Mar | Apr | May | Jun | July | Aug |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Woreda /Kebele selection |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Youth organization |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sit selection for construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| House construction |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide training & exchange visit |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Purchase equipment's |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Availing feed & vaccines |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Availing day old chicken |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Follow up & monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Dissemination of chicken |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |

[G] In the source, the responsibility column and all month cells are blank, and no year is given. Month names are retained exactly. This plan does not assume whether they refer to a Gregorian or an Ethiopian-calendar-aligned year (the Sep.-Aug. sequence matches Meskerem-Nehase). The project period (2018-2020) has elapsed. No evidence was provided that any activity took place, so the schedule is treated as proposed, not implemented.

### J2. Proposed phased implementation (new; relative months, Month 1 = the original 'Sep.' column) [A]

| Phase / months | Activities (link to original list) | Responsible | Budget (one enterprise) | Decision gate |
| --- | --- | --- | --- | --- |
| 0. Validation, M1-M2 (Sep.-Oct.) | Confirm project status, woredas/kebeles; buyer interviews; supplier quotations; group by-laws [Woreda/Kebele selection; Youth organization] | Project focal persons; coop office | Within project M&E | G0: prices quoted; >= 60 buyer interviews; site meets checklist |
| 1. Set-up, M2-M4 (Oct.-Dec.) | Legal registration; house construction; equipment purchase; training and exchange visit; vet plan [Sit selection; House construction; Training; Purchase equipment] | Woreda; chair; HU community service | Equipment cash 30,000; registration 3,000 | G1: house and vet sign-off; pre-orders >= 60% of batch; loan approved |
| 2. Pilot batch, M5-M6 (Jan.-Feb.) | Place 500 DOC; brood; vaccinate; sell [Availing feed & vaccines; DOC; Dissemination] | Production and sales leads | First batch ~ETB 132,500 (ETB 57,000 project in-kind) | G2: survival >= 85%; price >= break-even; 95% cash collected in 30 days |
| 3. Routine batches, M8, M11 ... | Batches every 3 months; follow-up of buyers [Follow up & monitoring] | Management committee | Self-financed from sales | Stop/adjust if any gate fails twice |
| 4. Review, M12 (Aug.) | Annual accounts; breed-preference survey [O monitoring]; decision on scale and vermicompost Phase 2 [Reporting] | General assembly; project | - | G3: continue / resize / exit |

### J3. Monitoring indicators

| Indicator | Frequency | Target | Source |
| --- | --- | --- | --- |
| Survival to sale per batch | Per batch | >= 90% | Batch card |
| Feed per pullet sold (kg) | Per batch | <= 1.9 | Feed stock card |
| Pullets sold / placed; unsold birds at 9 weeks | Per batch | 90% / 0 | Sales register |
| Average price vs break-even | Per batch | >= ETB 396 (PY1 prices) | Invoices |
| Repeat and referred buyers | Quarterly | >= 40% | Customer register |
| Gross margin per batch | Per batch | >= 30% | Batch P&L |
| Cash balance and receivables | Monthly | Cash > next batch DOC cost; receivables < 30 days | Bank reconciliation |
| Operating cost per pullet | Quarterly | Within 10% of plan | Accounts |
| Buyer-reported performance (survival, eggs) [O] | 6 and 12 months after sale | Evidence for breed choice | Checklist [O] |

## K. Environmental and social performance

Employment and inclusion: 20 young women across two enterprises [O]. The base case funds about 36 paid duty-days a month per enterprise [A] and gives members a share of profit.

Resource use: ~3.4 t feed, ~20 m3 water and modest electricity per enterprise per year [A].

Waste: ~8 t of used litter per year [A] is a resource for composting/vermicomposting, not waste. About 200 carcasses a year need hygienic disposal.

Odour, ammonia and runoff: dry litter management, ventilation, a covered litter store and no wash-water discharge to streams.

Worker safety: dust and ammonia exposure, zoonotic risk (HPAI), heavy lifting. Provide masks, gloves, handwashing and training; observe the Labour Proclamation's OSH duties (No. 1156/2019, text to verify).

Community effects: closer access to improved birds [O]; risk of spreading disease if biosecurity fails; women's income and skills.

Environmental screening: a ~35 m2 house is likely to fall into the lowest ESIA category under Proc. 1371/2025 [V: R25]. Confirm with the woreda/regional environment office.

No carbon credits or environmental payments are counted: there is no verified, accessible mechanism.

### Regulatory and licensing requirements (to verify)

| Requirement | Level | Status of evidence |
| --- | --- | --- |
| Legal registration of each youth group (cooperative or association) | Woreda cooperative office under federal cooperative law (Proc. 985/2016) | Named in original [O]; law text not retrieved |
| Commercial registration, trade licence, TIN | Federal law applied by regional/woreda trade offices; eTrade portal | Proc. 980/2016, amended 1150/2019 and again in 2025 (online registration) [V: R23, R24] |
| Business income tax | Federal law; regional revenue bureau administers | Category C abolished by Proc. 1395/2025 [V: R20]; gazettal status disputed [V: R21]; cooperative incentives unverified |
| VAT | Federal | Registration required above ETB 2 million turnover; 15% [V: R22]. Base PY5 turnover ETB 1.27 million is below the threshold, but NGO tenders may require VAT-registered suppliers [V: R15] |
| Veterinary drugs and feed | Federal authority under Proc. 728/2011 [V: R19] | Buy only registered products from licensed suppliers |
| Poultry farm registration/licensing | Proposed in 2018; current status unknown | Ask the regional livestock bureau |
| Environmental screening | Regional environment authority under Proc. 1371/2025 [V: R25] | Likely low category - confirm |

# 3. Annex - Original Data and Assumptions Register

Part A lists every important source value. Part B (new assumptions) is in Annex 4 with each assumption's status and source.

| ID | Item | Original value (as written) | Location | Use in plan | Issue / clarification |
| --- | --- | --- | --- | --- | --- |
| O1 | Title | BENEFIT REALISE Project HwU Cluster Work plan on Integrated Strategies for Resilience | Title | Context | - |
| O2 | Theme | 'Them: Livestock' | Title | Context | Typo ('Them') preserved |
| O3 | Activity | Small-scale poultry enterprises to promote dissemination of improved breeds and enhance youth employment | Title | Business concept | - |
| O4 | Programme | 'Realizing sustainable agricultural livelihood project' of BENEFIT; aligned with GoE PSNP | S.1 | Context, target group | - |
| O5 | Project period | three years (2018-2020) | S.1 | Timeline | Elapsed; implementation status unknown [G] |
| O6 | Breeds | Lohman Brown and Koekoek (Dawud et. al, 2018) | S.1 | Products | Spelling 'Lohman'; citation not verified; Lohmann Brown is a hybrid layer [G] |
| O7 | Location | two woredas; 'Two kebeles in two different woredas'; kebeles 'where there is electricity' | S.1, S.2, approach | Location criteria | Not named; region unclear [G] |
| O8 | Enterprises | Two model poultry enterprises | Approach | Scale | - |
| O9 | Members | 10 young female members per group / 10 unemployed young females | S.1, approach | Ownership, labour | Consistent |
| O10 | Production model | grow day-old-chicken for about two months and sell the pullets | Approach | Batch cycle | Chick numbers not stated [G] |
| O11 | Cost-sharing | House established by the woreda; project supplies DOC, brooder boxes, feeders and feed only for one month | Approach | Funding structure | Budget also funds house inputs (ETB 40,000) - partial support per activity list; reconcile [G] |
| O12 | Training | poultry management, team work, book keeping and accounting | Approach | Governance | - |
| O13 | Linkages | input suppliers (feed, vaccine, day-old-chicken), credit sources and market outlets | Approach | Sustainability | Prospective; none confirmed |
| O14 | Deliverables | 5 items incl. 'Site selection for house construction and poultry feed production' | Activities | Implementation | Feed production not described or budgeted [G] |
| O15 | Team | Implementing Clusters: Hawassa, Arsi, Woldiya University; Lead Cluster: Mekele University; Responsible Body: Gurmessa Umeta/ Asfaw Tafesse | S.2 | Governance | Relation of 3 clusters to a 2-woreda pilot unclear [G] |
| O16 | Schedule | 11 activities; months Sep.-Aug.; responsibility and month cells blank | S.3 | Implementation | No year; calendar not specified [G] |
| O17 | Engagement | HU community service department: technical support, training, exchange visits | S.4 | Support | - |
| O18 | Stakeholders | woreda PSNP office (youth selection); woreda agricultural cooperative development office (legal entity); Debrezeit Agricultural Reserch Center (DOC) | S.4.1 | Partners | Prospective |
| O19 | Dissemination | regional workshops; compiled and analysed reports | S.4.2 | Learning | - |
| O20 | Monitoring | planned vs achieved; activity-based budget tracking; breed-preference checklists | S.4.3 | M&E | - |
| O21 | Budget line | Procurument of industial inpout for Poultery house construction/renovation: 40,000 | S.5 | Baseline H1; per-enterprise split [A] | Unit quantities not stated |
| O22 | Budget line | Purchase of poultery feed/: 70,000 | S.5 | Baseline H1; per-enterprise split [A] | Unit quantities not stated |
| O23 | Budget line | Purchase of vaccsine / medicine: 12,000 | S.5 | Baseline H1; per-enterprise split [A] | Unit quantities not stated |
| O24 | Budget line | Purchase of equipments /brooder box, watering, feeder , saw dust etc: 30,000 | S.5 | Baseline H1; per-enterprise split [A] | Unit quantities not stated |
| O25 | Budget line | Provision of trainings ( Group formation, book keeping, Poltery production management: 28,000 | S.5 | Baseline H1; per-enterprise split [A] |  |
| O26 | Budget line | Conducting of exchange visites: 20,000 | S.5 | Baseline H1; per-enterprise split [A] |  |
| O27 | Budget line | Purchased of day old chikens: 32,000 | S.5 | Baseline H1; per-enterprise split [A] | Unit quantities not stated |
| O28 | Budget line | Monitoring and Evaluation: 68,000 | S.5 | Baseline H1; per-enterprise split [A] |  |
| O29 | Budget total | Total 300,000 | S.5 | Baseline | Reconciles with line items |

# 4. Annex - Financial projections (one enterprise, base case, nominal ETB)

Source: Poultry_Financial_Model.xlsx (Annual and Monthly sheets). All figures are [A]-based projections. The statements reconcile: the balance-sheet check and the cash check are zero in every year.

## 4.1 PY1 monthly cash flow (Month 1 = original 'Sep.' column; year not stated)

| ETB, PY1 | M1 Sep | M2 Oct | M3 Nov | M4 Dec | M5 Jan | M6 Feb | M7 Mar | M8 Apr | M9 May | M10 Jun | M11 Jul | M12 Aug | PY1 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cash collected | - | - | - | - | - | 121,500 | 81,000 | - | 121,500 | 81,000 | - | 121,500 | 526,500 |
| Variable costs paid | - | - | - | - | (29,200) | (46,300) | - | (86,200) | (46,300) | - | (86,200) | (46,300) | (340,500) |
| Fixed costs paid | - | (3,000) | - | (11,629) | (11,629) | (11,629) | (11,629) | (11,629) | (11,629) | (11,629) | (11,629) | (11,629) | (107,663) |
| Interest | - | - | - | (1,833) | (1,833) | (1,833) | (1,746) | (1,658) | (1,568) | (1,476) | (1,383) | (1,287) | (14,618) |
| Net operating cash flow | - | (3,000) | - | (13,462) | (42,662) | 61,738 | 67,624 | (99,487) | 62,003 | 67,895 | (99,212) | 62,283 | 63,719 |
| Cash-funded capex | - | - | (30,000) | - | - | - | - | - | - | - | - | - | (30,000) |
| Member equity | 20,000 | - | - | - | - | - | - | - | - | - | - | - | 20,000 |
| Loan disbursed | - | - | 100,000 | - | - | - | - | - | - | - | - | - | 100,000 |
| Principal repaid | - | - | - | - | - | (4,740) | (4,826) | (4,915) | (5,005) | (5,097) | (5,190) | (5,285) | (35,058) |
| Net cash flow | 20,000 | (3,000) | 70,000 | (13,462) | (42,662) | 56,998 | 62,798 | (104,402) | 56,998 | 62,798 | (104,402) | 56,998 | 118,661 |
| Closing cash | 20,000 | 17,000 | 87,000 | 73,538 | 30,875 | 87,873 | 150,671 | 46,269 | 103,267 | 166,065 | 61,663 | 118,661 |  |

## 4.2 Income statement

| ETB (nominal) | PY1 | PY2 | PY3 | PY4 | PY5 | PY1-5 |
| --- | --- | --- | --- | --- | --- | --- |
| Pullet sales | 607,500 | 907,200 | 1,016,064 | 1,137,992 | 1,274,551 | 4,943,306 |
| Total sales revenue | 607,500 | 907,200 | 1,016,064 | 1,137,992 | 1,274,551 | 4,943,306 |
| Day-old chicks | (150,000) | (224,000) | (250,880) | (280,986) | (314,704) | (1,220,569) |
| Feed | (204,000) | (304,640) | (341,197) | (382,140) | (427,997) | (1,659,974) |
| Vaccines and medication | (18,000) | (26,880) | (30,106) | (33,718) | (37,764) | (146,468) |
| Brooding energy | (9,000) | (13,440) | (15,053) | (16,859) | (18,882) | (73,234) |
| Litter and disinfectant | (4,500) | (6,720) | (7,526) | (8,430) | (9,441) | (36,617) |
| Selling and transport | (12,000) | (17,920) | (20,070) | (22,479) | (25,176) | (97,646) |
| Total variable costs | (397,500) | (593,600) | (664,832) | (744,612) | (833,965) | (3,234,509) |
| Gross margin | 210,000 | 313,600 | 351,232 | 393,380 | 440,585 | 1,708,797 |
| Member duty allowances | (81,000) | (120,960) | (135,475) | (151,732) | (169,940) | (659,108) |
| Water | (5,400) | (8,064) | (9,032) | (10,115) | (11,329) | (43,941) |
| Administration | (7,200) | (10,752) | (12,042) | (13,487) | (15,106) | (58,587) |
| Maintenance | (11,062) | (16,520) | (18,502) | (20,723) | (23,209) | (90,017) |
| Registration and licences | (3,000) | (2,240) | (2,509) | (2,810) | (3,147) | (13,706) |
| Total fixed operating costs | (107,662) | (158,536) | (177,560) | (198,868) | (222,732) | (865,358) |
| EBITDA excluding grants | 102,338 | 155,064 | 173,672 | 194,512 | 217,854 | 843,439 |
| Depreciation | (25,500) | (34,000) | (34,000) | (34,000) | (34,000) | (161,500) |
| Interest | (14,618) | (7,360) | - | - | - | (21,978) |
| Profit before grants and tax | 62,219 | 113,704 | 139,672 | 160,512 | 183,854 | 659,961 |
| Grant income - in-kind inputs (non-cash, one-off) | 57,000 | - | - | - | - | 57,000 |
| Income tax (placeholder 10%) | (11,922) | (11,370) | (13,967) | (16,051) | (18,385) | (71,696) |
| NET PROFIT | 107,297 | 102,334 | 125,705 | 144,461 | 165,468 | 645,265 |
| Memo: net profit excluding grant income | 50,297 | 102,334 | 125,705 | 144,461 | 165,468 | 588,265 |
| Memo: imputed unpaid member labour | 63,000 | 94,080 | 105,370 | 118,014 | 132,176 | 512,639 |
| Memo: economic profit after imputed labour, excl. grants | (12,703) | 8,254 | 20,335 | 26,447 | 33,293 | 75,626 |

## 4.3 Cash-flow statement

| ETB (nominal) | PY1 | PY2 | PY3 | PY4 | PY5 | PY1-5 |
| --- | --- | --- | --- | --- | --- | --- |
| Cash collected from customers | 526,500 | 897,480 | 1,005,178 | 1,125,799 | 1,260,895 | 4,815,851 |
| Variable costs paid in cash | (340,500) | (593,600) | (664,832) | (744,612) | (833,965) | (3,177,509) |
| Fixed costs paid | (107,662) | (158,536) | (177,560) | (198,868) | (222,732) | (865,358) |
| Interest paid | (14,618) | (7,360) | - | - | - | (21,978) |
| Income tax paid | - | (11,922) | (11,370) | (13,967) | (16,051) | (53,311) |
| Net cash from operations | 63,719 | 126,062 | 151,415 | 168,352 | 188,147 | 697,695 |
| Net cash from investing (cash-funded capex) | (30,000) | - | - | - | - | (30,000) |
| Member equity | 20,000 | - | - | - | - | 20,000 |
| Loan disbursed | 100,000 | - | - | - | - | 100,000 |
| Loan principal repaid | (35,058) | (64,942) | - | - | - | (100,000) |
| Additional funding required (source not identified) | - | - | - | - | - | - |
| Net cash from financing | 84,942 | (64,942) | - | - | - | 20,000 |
| Net change in cash | 118,661 | 61,121 | 151,415 | 168,352 | 188,147 | 687,695 |
| Closing cash | 118,661 | 179,781 | 331,196 | 499,549 | 687,695 |  |
| Lowest month-end cash in year | 17,000 | 49,760 | 119,318 | 262,245 | 421,915 |  |

## 4.4 Balance sheet

| ETB, end of year | PY1 | PY2 | PY3 | PY4 | PY5 |
| --- | --- | --- | --- | --- | --- |
| Cash | 526,500 | 897,480 | 1,005,178 | 1,125,799 | 1,260,895 |
| Trade receivables | 81,000 | 90,720 | 101,606 | 113,799 | 127,455 |
| Net fixed assets (incl. in-kind assets) | 269,500 | 235,500 | 201,500 | 167,500 | 133,500 |
| TOTAL ASSETS | 469,161 | 506,001 | 634,303 | 780,848 | 948,650 |
| Loan outstanding | 64,942 | - | - | - | - |
| Income tax payable | 11,922 | 11,370 | 13,967 | 16,051 | 18,385 |
| Total liabilities | 76,864 | 11,370 | 13,967 | 16,051 | 18,385 |
| Member paid-in capital | 20,000 | 20,000 | 20,000 | 20,000 | 20,000 |
| Contributed capital (grants, in-kind assets) | 265,000 | 265,000 | 265,000 | 265,000 | 265,000 |
| Additional funding required, cumulative (unsourced) | - | - | - | - | - |
| Retained earnings | 107,297 | 209,631 | 335,335 | 479,796 | 645,265 |
| Total equity | 392,297 | 494,631 | 620,335 | 764,796 | 930,265 |
| TOTAL LIABILITIES AND EQUITY | 469,161 | 506,001 | 634,303 | 780,848 | 948,650 |
| Check (assets - liabilities - equity) | - | - | - | - | - |

## 4.5 Assumptions (from the model; Base / Downside / Upside)

| Assumption | Unit | Base | Downside | Upside | Status / source / note |
| --- | --- | --- | --- | --- | --- |
| 1. Timing (model month 1 = 'Sep.' column of the original activity schedule; year not stated in source) |  |  |  |  |  |
| Month poultry house and equipment are ready | month | 3 | 4 | 3 | Assumption. Original Gantt cells are blank; sequence (selection > site > construction > training > inputs) implies construction precedes DOC. |
| Month of first day-old-chick (DOC) placement | month | 5 | 6 | 5 | Assumption (original: 'Availing day old chicken' listed after construction/training; timing blank). |
| Months between batch placements | months | 3 | 4 | 3 | Assumption: ~2 months rearing (original: 'about two months') + ~1 month sale, cleaning, rest. Base = 4 batches/yr. |
| Month member equity is paid in | month | 1 | 1 | 1 | Assumption. |
| 2. Production |  |  |  |  |  |
| DOC placed per batch | birds | 500 | 500 | 500 | ILLUSTRATIVE planning scale - the original proposal does not state chick numbers. ~25-30 m2 brooding/rearing floor at 15-20 birds/m2 to 8 weeks. VERIFY |
| Mortality to sale (~8 weeks) | % of placed | 10.0% | 20.0% | 7.0% | Assumption. On-farm Koekoek trial in South Omo reported 73.1% survival to 45 days (farmer management); managed brooding should do better. VERIFY |
| Feed per bird placed, 0-8 weeks (incl. wastage) | kg | 1.70 | 1.80 | 1.60 | Assumption from typical layer/dual-purpose pullet growth curves; confirm with breed guide (Lohmann Brown / Koekoek) and supplier. VERIFY |
| Share of batch feed used in placement month | % | 40.0% | 40.0% | 40.0% | Assumption (intake rises with age). |
| 3. Prices and variable costs (PY1 prices; escalated annually) |  |  |  |  |  |
| Day-old chick price | ETB/chick | 100 | 120 | 90 | Assumption. Published 2025-26 figures conflict (ETB 5-22 to 75); pre-2022 press reported ~ETB 50. Obtain quotes from DZARC (EIAR) and private hatcheries. VERIFY |
| Starter/grower feed price | ETB/kg | 80 | 95 | 75 | Assumption. 2022 field data: layer feed mean ETB 2,695/qt (26.95/kg); 2026 vendor web page: ETB 8,800/qt (unverified). Birr has depreciated sharply since July 2024. VERIFY |
| Vaccines and medication | ETB/bird placed | 12 | 15 | 10 | Assumption (NVI vaccines: Marek's at hatchery, NCD, Gumboro, fowl pox). VERIFY |
| Brooding energy (electricity/backup) | ETB/batch | 3,000 | 4,000 | 2,500 | Assumption. VERIFY |
| Litter (sawdust) and disinfectant | ETB/batch | 1,500 | 2,000 | 1,200 | Assumption (original budget line mentions saw dust). VERIFY |
| Selling and transport | ETB/batch | 4,000 | 6,000 | 3,500 | Assumption. VERIFY |
| Selling price of ~8-week pullet | ETB/bird | 450 | 380 | 520 | Assumption. Only located 2026 data point: one online listing of a vaccinated 2-month Bovans Brown at ETB 710 (Addis, undated); 2020 report: ETB 100-120. Rural PSNP buyers' willingness to pay must be tested. VERIFY |
| Share of sales collected in month of sale | % | 60.0% | 40.0% | 80.0% | Assumption; remainder collected the following month (institutional/NGO buyers pay on invoice). |
| Annual selling-price escalation | %/yr | 12.0% | 8.0% | 12.0% | Assumption. CPI inflation 15.3% (Jul 2026); NBE expects decline. Downside: prices lag costs. |
| Annual cost escalation | %/yr | 12.0% | 15.0% | 12.0% | Assumption (see above). |
| 4. Fixed operating costs (PY1 prices) |  |  |  |  |  |
| Cash allowance for members on duty | ETB/month | 9,000 | 9,000 | 9,000 | Assumption: 3 members on rotating duty x ETB 3,000/month. Remaining members are unpaid owners (see memo). |
| Imputed value of unpaid member time (memo only) | ETB/month | 7,000 | 7,000 | 7,000 | Assumption: 7 members x 4 days/month x ETB 250/day. Not a cash cost; shown to reveal economic return to labour. VERIFY |
| Water | ETB/month | 600 | 800 | 600 | Assumption. VERIFY |
| Bookkeeping, phone, stationery, bank charges | ETB/month | 800 | 800 | 800 | Assumption. |
| Maintenance | % of asset cost/yr | 5.0% | 5.0% | 5.0% | Assumption. |
| Legal registration (one-off, month 2) | ETB | 3,000 | 3,000 | 3,000 | Assumption; group organised as cooperative/association via woreda cooperative office. VERIFY |
| Annual licence/renewal and audit | ETB/yr | 2,000 | 2,000 | 2,000 | Assumption. VERIFY |
| 5. Investment and grant/in-kind contributions |  |  |  |  |  |
| Poultry house - full value (woreda in-kind incl. project materials) | ETB | 250,000 | 250,000 | 250,000 | Assumption for valuing the woreda contribution (~35 m2 simple house). Original: woreda builds house; project supplies corrugated iron and nails. VERIFY |
| Equipment (brooders, feeders, drinkers, heaters, scale) at 2026 prices | ETB | 45,000 | 50,000 | 45,000 | Assumption. VERIFY |
| Project grant: equipment (original ETB 30,000 / 2 groups) | ETB | 15,000 | 15,000 | 15,000 | ORIGINAL budget line split equally between the two enterprises - the equal split is an analytical assumption. |
| Project grant: first-batch inputs (DOC 16,000 + feed 35,000 + vaccine 6,000) | ETB | 57,000 | 57,000 | 57,000 | ORIGINAL budget lines (32,000; 70,000; 12,000) split equally. Original: feed 'only for one month'. |
| Useful life - house | years | 10 | 10 | 10 | Assumption. |
| Useful life - equipment | years | 5 | 5 | 5 | Assumption. |
| 6. Financing, tax and appraisal |  |  |  |  |  |
| Minimum cash buffer to maintain | ETB | 5,000 | 5,000 | 5,000 | Assumption; any shortfall below this is shown as additional funding required. |
| Member cash equity (10 members x ETB 2,000) | ETB | 20,000 | 20,000 | 20,000 | Assumption. VERIFY |
| Working-capital loan disbursement month | month | 3 | 3 | 3 | Assumption. |
| Working-capital loan | ETB | 100,000 | 100,000 | 100,000 | Assumption (MFI / youth revolving fund). Original proposal: 'facilitate linkage with credit sources' - no loan secured. |
| Loan interest rate | %/yr | 22.0% | 26.0% | 20.0% | Assumption. NBE policy rate raised to 16% (13 Jul 2026) and credit-growth cap removed; MFI rates typically higher. VERIFY |
| Grace period (interest only) | months | 2 | 2 | 2 | Assumption. |
| Repayment period after grace | months | 18 | 18 | 18 | Assumption. |
| Monthly instalment (computed) | ETB/month | computed |  | 6,573 | Formula. |
| Business income tax provision on profit | % of PBT | 10.0% | 10.0% | 10.0% | PLACEHOLDER. Income Tax (Amendment) Proc. 1395/2025 abolished Category C; cooperative/MSE incentives may apply. Confirm with Sidama/regional revenue bureau. VERIFY |
| Discount rate (nominal) | % | 25.0% | 25.0% | 25.0% | Rationale: NBE policy rate 16% + CPI ~15% => bank lending ~18-22%; plus premium for a start-up, perishable-livestock enterprise. |

# 5. Annex - Current-market comparison with original figures

| Parameter | Original proposal [O] | Current information (Oct 2026) | Implication |
| --- | --- | --- | --- |
| Exchange rate | Not stated (2018-2020) | ~160-164 ETB/USD, Sep-Oct 2026 [V: R6, R7]; floated July 2024 | Imported genetics, vaccines, feed ingredients and iron sheets cost several times more in birr |
| Inflation | Not stated | 15.3% y/y July 2026, up from 9.7% in Feb 2026 [V: R2, R5] | Re-price each batch; 12%/yr escalation in model |
| Interest rates | Not stated ('credit sources') | NBE policy rate 16% (13 Jul 2026); lending caps removed [V: R3] | 22% assumed loan rate; verify with MFIs |
| DOC | ETB 32,000 total; numbers not stated | ~ETB 50 pre-2024 [V: R11]; plan ETB 100 [A] | Original line buys ~320 chicks at plan price |
| Feed | ETB 70,000 for one month | ETB 2,695/qt in 2022 [V: R10]; plan ETB 8,000/qt [A] | Feed is ~51% of variable cost |
| Pullet price | Not stated | ETB 100-120 (2020) [V: R13]; ETB 710 Addis listing [V: R12]; plan 450 [A] | Largest single uncertainty |
| Equipment | ETB 30,000 (two groups) | Plan ETB 45,000 per group [A] | Original covers ~1/3 of need |
| House | Woreda builds; ETB 40,000 inputs | Plan full value ETB 250,000 [A] | Must be confirmed by woreda in writing |
| Income tax | Not addressed | Proc. 1395/2025 reform; Category C dissolved [V: R20, R21] | Confirm with revenue bureau |
| VAT | Not addressed | Threshold ETB 2 million; 15% [V: R22] | Below threshold; tender eligibility issue |
| Institutional demand | Not addressed | NGO tenders for 45-day pullets, Aug 2026 [V: R14, R15] | Sales channel to pursue |

# 6. Annex - Prioritised missing information and validation tasks

| # | Task | Why | By |
| --- | --- | --- | --- |
| 1 | Confirm whether the pilot was implemented (2018-2020) and what assets exist now | Determines stage: start-up vs operating vs restart | Project focal persons |
| 2 | Name the two woredas and kebeles; confirm region and electricity | Location-specific prices, regulators, security | Project / woreda |
| 3 | Written quotations: DOC (DZARC and a private hatchery), starter/grower feed, vaccines, equipment, iron sheets | Replace [A] costs | Chair, treasurer |
| 4 | 60 buyer interviews + pre-order campaign; contact NGOs running pullet tenders | Validate price and demand | Sales lead, DA |
| 5 | Woreda letter confirming the house (size, value, timing) and land-use right | In-kind contribution; collateral | Woreda |
| 6 | Allocation of the ETB 300,000 between the two enterprises and project costs | Per-enterprise funding | Project |
| 7 | Vaccination schedule and service agreement with woreda vet | Survival target | Production lead |
| 8 | Legal form, registration, tax category and incentives | Compliance, tax cost | Coop office, revenue bureau |
| 9 | Lender term sheet (amount, rate, tenor, collateral, group guarantee) | Working capital | Treasurer |
| 10 | Decide breed per segment (Koekoek vs Lohmann Brown; sexed chicks) | Customer fit; cockerel problem | Project + HU |
| 11 | Verify Dawud et al. (2018) and obtain HU breed-performance data | Evidence base | HU |
| 12 | Clarify 'poultry feed production' and the role of Arsi/Woldiya/Mekele clusters | Scope | Project |

# 7. Conclusion

The concept is sound and the work plan provides a useful start-up subsidy. As written, though, the proposal cannot show commercial viability. At Oct 2026 planning prices, a 500-bird, four-batch enterprise can cover its costs and repay a small working-capital loan if it sells at ETB 396 or more per pullet and keeps survival above about 79%. Neither has been tested. Decision: pilot first (one or two batches with the original grant inputs and pre-orders), then decide at Gate G2 whether to operate commercially, resize or exit.

# 8. Annex - References (dated, with links; accessed 22-23 Oct 2026)

| Ref | Source | Date | Link | Use / caveat |
| --- | --- | --- | --- | --- |
| R1 | Original proposal: 'BENEFIT REALISE Project HwU Cluster Work plan on Integrated Strategies for Resilience - Theme: Livestock - Small-scale poultry enterprises ...' (file HwU_Cluster_work_plan_for_pilot_study.docx) | Undated (project period stated as 2018-2020) | Supplied by the user | Sole source of [O] data. |
| R2 | Capital Ethiopia, 'Ethiopia's growth paradox ...' (annual inflation 15.3% in July 2026; food 15.7%; non-food 14.8%) | 6 Sep 2026 | https://capitalethiopia.com/2026/09/06/ethiopias-growth-paradox-is-the-fastest-growing-economy-in-africa-also-its-most-fragile/ | Inflation; cites Ethiopian Statistical Service. |
| R3 | Ecofin Agency, 'Ethiopia drops bank lending caps, raises rates to keep inflation in check' (NBE policy rate 15% to 16%, 13 Jul 2026) | Jul 2026 | https://www.ecofinagency.com/news-finances/1407-57359-ethiopia-drops-bank-lending-caps-raises-rates-to-keep-inflation-in-check | Financing cost. |
| R4 | Trading Economics, 'Ethiopia Lifts Key Policy Rate to 16%' | Jul 2026 | https://tradingeconomics.com/ethiopia/interest-rate/news/566412 | Corroborates R3. |
| R5 | Ecofin Agency, 'Ethiopia keeps tight monetary policy as inflation falls to 9.7%' (Feb 2026 reading) | Apr 2026 | https://www.ecofinagency.com/news-finances/0104-54322-ethiopia-keeps-tight-monetary-policy-as-inflation-falls-to-9-7-and-growth-remains-strong | Inflation trend. |
| R6 | Trading Economics, Ethiopian birr quote (about 163.9 ETB/USD on 22 Oct 2026; down ~20% over 12 months) | 22 Oct 2026 | https://tradingeconomics.com/ethiopia/currency | Exchange rate. Not an NBE official rate. |
| R7 | Dashen Bank, daily exchange rates (USD buying 160.5377 / selling 163.7485 birr) | 5 Sep 2026 | https://dashenbanksc.com/daily-exchange-rates/ | Commercial-bank rate. |
| R10 | Production Performance and Profitability of Small-scale Commercial Poultry Farms in Arsi and East-Showa Zones (J. World Poult. Res. 14(1): 41-54) | 2024 (2022 data) | https://jwpr.science-line.com/attachments/article/78/JWPR14(1)41-54,2024.pdf | Layer feed mean ETB 2,695/qt (range 1,800-4,000) in 2022. |
| R11 | Addis Fortune, 'Feed, forex shortages threaten poultry farms' (feed ETB 2,950/qt; chick price ~ETB 50) | Date not confirmed (pre-2024) | https://addisfortune.news/feed-forex-shortages-threaten-poultry-farms | Historical price reference only. |
| R12 | Jiji.com.et livestock and poultry listings (2-month vaccinated Bovans Brown at ETB 710) | Listing undated | https://jiji.com.et/livestock-and-poultry | Single retail asking price, Addis Ababa; weak evidence. |
| R13 | Dutch-Africa Poultry / ENTAG, 'Business Opportunity Report - Poultry Ethiopia' (pullets ETB 100-120) | Feb 2020 | https://dutchafricapoultry.com/wp-content/uploads/2021/10/PoultryBOR_Ethiopia022020_ENTAG.pdf | Price at the time of the original proposal. |
| R14 | Reporter Tenders: World Vision Ethiopia bid for 45-day-old Sasso pullets and day-old chicks (closing 21 Aug 2026; prices incl. VAT) | Aug 2026 | https://reportertenders.com/bids/world-vision-ethiopia-currently-wants-to-invite-eligible-bidders-to-participate-in-the-bid-floated-for-45-days-old-pullets-sasso-breed-and-day-old-chicken-with-sasso-breed/ | Evidence of institutional pullet demand; no prices published. |
| R15 | Reporter Tenders: Development Expertise Centre bid for 45-day pullets (Bovans Brown/Lohmann and Sasso; 15% VAT; closing 12 Aug 2026) | Aug 2026 | https://reportertenders.com/bids/development-expertise-centre-bid-announcement-bid-for-procurement-of-shoat-goat-sheep-poultry-pullet-chicken-and-agricultural-input-horticulture-products-about-dec/ | As R14. |
| R16 | Hendrix Genetics - distributor page: EthioChicken, distributor of Bovans and Sasso day-old chicks in Ethiopia | Undated | https://layinghens.hendrix-genetics.com/en/distributors/ethiochicken/ | Alternative DOC source. |
| R17 | ILRI, 'Photo story: process of introducing chicks of selected strains in Ethiopia' (ACGG hatchery at Debre Zeit ARC; Koekoek chicks vaccinated for Marek's) | Undated (ACGG project era) | https://www.ilri.org/news/photo-story-process-introducing-chicks-selected-strains-ethiopia | DOC source named in original. |
| R18 | Isolation of genotype VII velogenic Newcastle disease virus from commercial farms in central Ethiopia, distinct from local vaccine strains (PMC11360104) | 2024 | https://www.ncbi.nlm.nih.gov/pmc/articles/PMC11360104/ | Disease risk despite vaccination. |
| R19 | Veterinary Drug and Feed Administration and Control Proclamation No. 728/2011 (UNEP LEAP record) | 2011 | https://leap.unep.org/en/countries/et/national-legislation/veterinary-drug-and-feed-administration-and-control-proclamation | Feed and veterinary drug control. |
| R20 | EY Tax News, 'Ethiopia issues a new income tax proclamation' (Income Tax (Amendment) Proclamation No. 1395/2025; Category C dissolved; Category A > ETB 2 million turnover) | 17 Dec 2025 | https://taxnews.ey.com/news/2025-2542-ethiopia-issues-a-new-income-tax-proclamation | PwC (reviewed 15 Jul 2026) states gazette publication still pending - status to verify. |
| R21 | PwC Worldwide Tax Summaries - Ethiopia, significant developments | Reviewed 15 Jul 2026 | https://taxsummaries.pwc.com/ethiopia/individual/significant-developments | As R20. |
| R22 | EY Tax News, 'Ethiopia introduces new VAT Proclamation' (Proc. No. 1341/2024; registration threshold ETB 2,000,000; standard rate 15%) | 16 Sep 2024 | https://taxnews.ey.com/news/2024-1698-ethiopia-introduces-new-vat-proclamation-introducing-raft-of-changes | VAT. |
| R23 | Capital Ethiopia - report on amended Commercial Registration and Business Licensing Proclamation (online registration; lease proof dropped) | Oct 2025 | https://capitalethiopia.com/?p=24588 | Proclamation number of the amendment not confirmed. Base law Proc. 980/2016, amended by Proc. 1150/2019. |
| R24 | Ministry of Trade and Regional Integration - eTrade online registration and licensing portal | Live portal | https://etrade.gov.et | Registration route; coverage not universal. |
| R25 | Environmental and Social Impact Assessment Proclamation No. 1371/2025 (UNEP LEAP record) | 2025 | https://leap.unep.org/en/countries/et/national-legislation/environmental-and-social-impact-assessment-proclamation-no | Screening categories set by directive; replaces Proc. 299/2002. |
| R31 | Global Living Wage Coalition, 'Living income report for rural Sidama, Ethiopia' (update) | Sep 2025 | https://www.globallivingwage.org/living-wage-benchmarks/living-income-report-for-rural-sidama-ethiopia/ | Income benchmark (definitions to be read in full). |
| R32 | Kana TV, 'Ethiopia's development bank to offer cheap loans to women and war-affected regions' | Jun 2026 | https://kanatelevision.com/news/ethiopia-s-development-bank-to-offer-cheap-loans-to-women-and-war-affected-regions-that-normally/ | Possible concessional credit line. |
| R33 | Addis Fortune, report on Sidama Microfinance Institution receiving a banking licence | Date not confirmed | https://addisfortune.news/?p=24313 | Local lender landscape. |
| R34 | IAU HESD portal, 'BENEFIT-REALISE Programme' (three-year Dutch-funded programme aligned with PSNP) | Undated | https://iau-hesd.net/action/benefit-realise-programme | Programme context (no pilot results found). |
| R35 | FAO, 'Livestock Country Review - Poultry Sector Ethiopia' (reliable commercial feed price data lacking) | 2019 | https://openknowledge.fao.org/server/api/core/bitstreams/eb7f69d5-57e6-465b-8846-4f950620e4ae/content | Data limitation. |
| R36 | Lohmann Breeders, Management Guide - cage housing: 'Body weight development and feed consumption' table | Current e-guide | https://lohmann-breeders.com/e-guide/cage-housing/18/ | Reference for feed per pullet (values not extracted - verify). |
| R37 | Hawassa University ETD repository - MSc thesis comparing Bovans, Koekoek and Sasso under traditional management, Boricha woreda, Sidama | Undated | https://etd.hu.edu.et/handle/123456789/1419 | Search-indexed; confirm the record matches before citing externally. |

Laws referred to but not retrieved in this research session (verify current text and status):

Labour Proclamation No. 1156/2019 (employment terms, occupational safety and health) - text not retrieved in this research session.

Cooperative Societies Proclamation No. 985/2016 (legal form for youth groups registered through the woreda cooperative office) - text not retrieved.

Commercial Registration and Business Licensing Proclamation No. 980/2016 as amended by Proc. No. 1150/2019 and a later amendment reported in Oct 2025 (R23).

Solid Waste Management Proclamation No. 513/2007 and Environmental Pollution Control Proclamation No. 300/2002 - text not retrieved; check current status.

Research limitations: several hosts (cgspace.cgiar.org, technoserve.org, selinawamucii.com) could not be opened from the research environment. Figures from them come from search-indexed text and are flagged. No supplier quotations, customer commitments, laboratory results or official price series specific to the project woredas were available. Every [A] value must be replaced by local evidence before lending decisions.