Integrated Vermicompost Unit

Business plan for a NEW component proposed alongside the youth pullet-rearing enterprises of the BENEFIT-REALISE HwU Cluster pilot

| Item | Detail |
| --- | --- |
| Document status | Draft for validation - new proposal; not part of the original work plan |
| Preparation date / research cut-off | 23 October 2026 / 23 October 2026 |
| Basis | No vermicompost proposal was supplied. The only original information used is shared with the poultry work plan (R1): the youth groups, sites, cost-sharing approach, saw-dust litter, HU support and the Sep.-Aug. schedule. |
| Companion files | Vermicompost_Financial_Model.xlsx; Poultry_Business_Plan.docx; Poultry_Financial_Model.xlsx |

Evidence labels: [O] original poultry work-plan information ¦ [V] verified current information with dated reference ¦ [A] new assumption ¦ [G] gap or contradiction. Because this component is new, every production, price, cost and funding figure is [A] unless a reference is given. Nothing here exists yet: no site, beds, earthworms, buyers, laboratory, lender or grant.

# 1. Diagnostic: is there an original proposal to assess?

No. The attached document is a poultry pilot work plan with no vermicompost content. As requested, this plan builds a vermicompost component 'accordingly': it uses the poultry enterprises' sites, members and used litter as a starting point. What the original work plan supplies, and what it lacks, for this purpose:

| Original element [O] | Relevance to vermicompost | Gap [G] |
| --- | --- | --- |
| Two youth groups of 10 young women | Possible owners/operators | Members have not agreed to a second business |
| Poultry houses in kebeles with electricity; litter with 'saw dust' in equipment line | Site, store and a feedstock (used litter) | Woredas/kebeles unknown; litter quantity unknown |
| HU community service department for training and exchange visits | Possible technical support | No vermicompost expertise or commitment stated |
| Linkage to credit sources and market outlets | Possible financing/marketing channel | Prospective only |
| Schedule Sep.-Aug., year not stated | Timing alignment | No year; activity cells blank |

# 2. Business plan

## A. Executive summary

Opportunity. Soil fertility decline and high mineral-fertiliser costs have drawn attention to vermicompost in Ethiopia. Recent work in the Rift Valley and Sidama documents active producers and buyers [V: R8, R9]. Each poultry enterprise would produce ~8 t a year of used litter [A]. Pre-composted with cattle manure and crop residues, it can feed earthworm (Eisenia fetida) beds [V: R28, R29].

Proposal [A]. One vermicompost unit per enterprise: Phase 1 has 16 lined ground beds (48 m2) under a ~120 m2 shade. Phase 2 adds 16 beds in PY2, subject to a decision gate. At full operation the unit processes ~109 t of raw feedstock a year, only 8 t of it poultry litter. It sells ~21 t of screened vermicompost at a blended ETB 16/kg in 25 kg bags (PY1 prices), plus a small volume of earthworms.

Investment and funding [A]. Phase 1 capex ETB 128,000; Phase 2 ETB 85,000 (PY1 prices); starter worms ETB 10,800. Base funding: member equity ETB 20,000 and a ETB 120,000 loan (not identified). The model shows a further ETB 318,974 of funding with no identified source (PY1 100,174; PY2 182,616; PY3 36,185). Slow market and worm ramp-up keeps the unit loss-making until PY3.

Financial outlook (base). Sales grow from ETB 40,213 (PY1) to ETB 550,663 (PY5). EBITDA is negative in PY1-PY2 ((77,759); (24,690)) and positive from PY3 (78,661). Five-year net profit is ETB (7,795). Full-cost NPV at 25% is ETB (147,559) (IRR 5%). The break-even price at PY3 volume is ETB 15.4/kg against a base price of ETB 16. Volume margin of safety is 6%.

Sensitivity. Each of these alone turns the five-year result clearly negative: a lower price (ETB 12/kg), lower demand (12 t/yr), paid-for feedstock at ETB 1.0/kg, or a 4-month cycle. The upside case (ETB 20/kg, cheap feedstock, 30 t demand) gives NPV ETB 306,859.

Recommendation: REDESIGN AND PILOT - do not borrow yet. The evidence does not support a loan-financed 32-bed unit at present. Recommended path: (1) Build Phase 1 at the lowest cost, or start with 4-6 beds, funded by members' equity or a grant, not debt. (2) Run two production cycles to measure actual conversion, labour and quality. (3) Sell the pilot output to named buyers at ETB 16/kg or more. (4) Expand only if a buyer list for at least 10 t/yr exists, realised price is at least ETB 16/kg and free or near-free feedstock is secured. Environmental benefits (waste reuse, soil organic matter) are real but do not make the unit financially viable on their own.

## B. Enterprise description and objectives

| Attribute | Proposal [A] | Comment |
| --- | --- | --- |
| Ownership | Same youth group as the poultry enterprise, as a second business line (or a separate group) | Members must decide; separate accounts recommended |
| Legal form | Activity added to the group's registration/licence | Verify licence category [G] |
| Stage | Concept / start-up; nothing built |  |
| Site | Next to the poultry house: shared store, water, guard; 300-400 m2 incl. pre-composting bay | Plot allocation needed from kebele/woreda |
| Scale | Phase 1: 16 beds (1 m x 3 m x 0.5 m); Phase 2: +16 beds | Gate at end of PY1 |
| Labour | 1 paid member-worker (Phase 1) + 0.5 (Phase 2); casual labour for screening; supervision by poultry duty members | Integration lowers labour cost |

Objectives [A]: (1) turn poultry litter and local organic residues into a saleable soil amendment; (2) create additional paid work for members; (3) supply nurseries and farmers with a consistent, labelled product. Measurable targets (PY3): ≥ 20 t saleable output; ≥ 85% bed utilisation; ≥ 2 laboratory tests a year passing internal specifications; ≥ 60% of volume to repeat buyers; price ≥ ETB 16/kg in PY1 terms.

Location requirements [A]: shade and protection from heavy rain; temperature within 15-35 C and bed moisture of 60-70% [V: R28]; reliable water (roof-water harvesting plus a tap); feedstock within 5 km; buyers (nurseries, horticulture) within 30 km; well-drained ground away from streams.

## C. Vermicompost market and competition

There are no verified customer commitments. The segments below are hypotheses to test through interviews, demonstrations and pilot sales.

| Segment | Likely use and quantity (to verify) | Requirements | Payment / season |
| --- | --- | --- | --- |
| Public and private seedling nurseries (forestry, coffee, fruit) | Potting mix; 1-4 t per nursery a year | Fine screened, mature, weed-free, consistent moisture | Budget cycle; peak before potting (Dec.-Mar.) |
| Horticulture producers (vegetables, fruit, ornamentals) | Nursery beds and transplant holes; 100-500 kg each | Consistent quality; delivery | Cash; before belg/kiremt planting |
| Smallholders (incl. PSNP households) | Kitchen gardens; 20-50 kg | Low price; small packs; proof of effect | Cash, small amounts; Jan.-May |
| Agro-dealers and urban gardeners/landscapers | Retail resale in 5-25 kg bags | Branding, labels, credit | 30-day credit |
| Projects/NGOs (ISFM, nutrition gardens) | Demonstration and distribution | Test results, invoices, VAT status | Tender-based |

### Prices and alternatives (consistent units: ETB per kg unless stated)

| Product | Price | Basis / date | Source |
| --- | --- | --- | --- |
| Vermicompost to households | ~10 (ETB 1,000/qt) | Rift Valley districts, Oct 2025 | R8 [V] |
| Vermicompost via local collectors | ~16 (ETB 1,600/qt) | Same | R8 [V] |
| Vermicompost (agribusiness note) | USD 17 per 100 kg | Undated; FX not stated | R39 |
| Vermicompost production cost (research estimate) | ~2.13 (ETB 2,130/t) | NW Ethiopia study | R38 |
| Earthworms (producer) | 300-500 per kg | Oct 2025 | R8 [V] |
| Earthworms (collectors' resale) | 600-800 per kg | Oct 2025 | R8 [V] |
| This plan: blended ex-site price | 16 (12 / 20) | PY1, incl. 25 kg bag | [A] |
| Farm-made compost / manure | Often free or bartered; no market price found | - | [G] |
| Mineral fertiliser (NPS, urea) | Not verified in this research | - | [G] - obtain cooperative union price |

Moisture is rarely stated in local price quotes. This plan sells at a declared ~40% moisture, so prices from other sources may not be strictly comparable [G]. Mineral fertiliser and vermicompost are not substitutes per kg of nutrient. The plan does not claim vermicompost replaces mineral fertiliser.

### Accessible demand estimate (transparent; to validate)

| Segment | Low (t/yr) | Base (t/yr) | High (t/yr) | Basis [A] |
| --- | --- | --- | --- | --- |
| Nurseries | 6 | 12 | 16 | Low 2x3 t; base 2 public x 4 t + 4 private x 1 t; high 3x4 t + 4x1 t |
| Horticulture producers | 3 | 6 | 8 | 15 / 30 / 40 growers x 200 kg |
| Smallholders | 2 | 3 | 4 | 70 / 100 / 130 adopters x 30 kg |
| Agro-dealers, urban, projects | 1 | 1 | 2 |  |
| Total accessible demand | 12 | 22 | 30 | Model input |

The model applies 40% of base demand in PY1 and 70% in PY2 (market development) and a seasonal profile peaking in Jan.-May [A]. Planned PY3 sales of 21.0 t are roughly equal to base demand, so the plan is demand-constrained. Validation tasks: visit all nurseries within 30 km, record their current inputs and prices, and run 10 demonstration plots or pots with nurseries and DAs before PY1 sales.

### Competition

Household and cooperative vermicompost producers promoted by NGO/ISFM programmes, mainly in Sidama and the Rift Valley [V: R8, R9]; co-operative-led sales and dry-season production were found financially unviable (BCR < 1) [V: R8].

Farm-made compost and manure (low cost, but bulky, variable and often weedy).

Mineral fertiliser (different function; subsidised supply channels).

Advantages of this unit: steady feedstock from the poultry enterprise, a screened and bagged product, batch testing and a site already staffed daily.

## D. Products and value proposition

| Product | Specification [A] | Status |
| --- | --- | --- |
| Screened vermicompost (core) | Mature, earthy odour, < 6 mm screen, ~40% moisture (declared), no visible contaminants; 25 kg bags (5 kg packs optional) | Base revenue |
| Earthworms (E. fetida) | Live worms with bedding, sold by weight from PY2 | Small base revenue (30 kg/yr); thin market |
| Vermiwash | Liquid prepared deliberately by passing water through an active, mature bed column; requires its own quality testing | Optional - excluded from base revenue |
| Bed drainage leachate | Uncontrolled run-off from beds; may contain pathogens and unstable compounds | Not a product - collect and return to pre-composting |
| Training/demonstrations | Short courses for farmers or projects | Optional, only on request |

Value proposition: 'Consistent, tested, bagged organic soil amendment made locally from managed poultry litter and manure.' No nutrient content, yield increase or certification is claimed until laboratory results and field demonstrations exist. Labels should state only the product name, net weight, moisture, batch number, producer and test results once available.

## E. Technical feasibility and production operations

| Element | Practice [A unless referenced] |
| --- | --- |
| Feedstocks | Poultry litter from own enterprise (droppings + sawdust); cattle manure from neighbouring households; crop residues; coffee pulp where locally available (seasonal). Collection by cart; written supply arrangements (cash or barter for compost). |
| Acceptance criteria | No plastics, glass, metal, treated wood or human waste; no feedstock from flocks culled for disease; no manure from animals treated with dewormers in the last 7-14 days; record source and date. |
| Pre-composting | Mandatory for poultry litter (ammonia and salts kill worms) [V: R29, R30]: mix ~1 part litter to 2-3 parts manure/residue by volume; heap 2-4 weeks with turning; ready when temperature falls to < 30 C and there is no ammonia smell. |
| Earthworms | Eisenia fetida [V: R28]; buy ~24 kg from a verified producer (identity checked); quarantine bed first; stock ~0.5 kg/m2 and multiply during a 6-month ramp-up. |
| Beds and shelter | 16 lined ground beds 1 x 3 x 0.5 m with slight slope and drainage channel to a leachate pit; ~120 m2 shade (poles + corrugated iron); bird, ant and mole protection (mesh, ash/water moats). |
| Management | Moisture 60-70% (squeeze test), temperature 15-35 C [V: R28]; feed in thin layers; cover with sacks/grass; watch for ants, rats, birds, flatworms. |
| Cycle and harvest | ~3 months per bed incl. harvest; light-separation or migration harvest; air-dry to ~40% moisture; screen at 6 mm; return oversize and worm-rich material. |
| Storage and packing | Shaded, dry store; 25 kg woven bags with liner; first-in-first-out; maximum ~3 months' stock. |
| Quality | Two laboratory tests a year (pH, EC, organic C, N, P, K, C:N, moisture, E. coli/Salmonella) at an accredited soil lab [G: lab not identified]; batch numbers and harvest dates on every bag; retain a 1 kg sample per batch. |
| Safety and environment | Gloves, boots and masks when handling raw litter; handwashing; tetanus vaccination advice; leachate captured, not discharged; odour controlled by pre-composting and cover. |

### Material-flow calculation (base, full operation PY3) [A]

| Step | Factor | Per kg raw | PY3 tonnes | Note |
| --- | --- | --- | --- | --- |
| Raw feedstock collected | - | 1.000 | 108.8 | of which poultry litter 8.0 t, other 100.8 t |
| Pre-composting loss (water + CO2) | 25% of raw | -0.250 | 27.2 |  |
| Bed feed (fresh) |  | 0.750 | 81.6 | 30% dry matter |
| Vermicomposting: DM loss 35%; product at 40% moisture | x 0.325 | 0.244 | 26.1 | Unscreened harvest (lagged one cycle) |
| Screening rejects (returned) | 10% of harvest | -0.024 | 2.6 | Not sold |
| Retained bedding/inoculum | 10% of harvest | -0.024 | 2.6 | Not sold |
| Saleable vermicompost |  | 0.195 | 20.9 | => 5.13 kg raw per kg saleable |

Reconciliation. Bed capacity: 32 beds x 85% utilisation x 750 kg / 3 months = 6,800 kg feed a month, i.e. ~81.6 t a year, matching the model's 81.6 t. Feedstock: the poultry enterprise supplies only ~7% of raw needs. The remaining ~101 t a year needs the collectable manure of roughly 25-40 local cattle, or coffee pulp/crop residues [A]. Farmers also need that manure, so this is the critical technical risk and must be secured by written arrangement before Phase 2. Labour: ~1.5 FTE plus casual screening labour is consistent with ~27 t a year of harvest handling. Water: ~2-4 m3 a month for 32 beds [A], partly from roof harvesting.

## F. Marketing and sales strategy

| Element | Approach [A] |
| --- | --- |
| Pricing | Bulk to nurseries ~ETB 13/kg; bagged to horticulture/agro-dealers ~ETB 19/kg; blended ETB 16 (PY1). Floor = break-even ETB 15.4/kg at planned volume. Earthworms ETB 350/kg. |
| Demonstrations | 10 nursery/pot or farmer plots in PY1 with DAs; open days at the poultry site; side-by-side photos; no yield claims beyond observed results. |
| Channels | Direct to nurseries (annual supply agreement), 2-3 agro-dealers on 30-day credit, farmer groups via DAs, project tenders. |
| Promotion budget | ETB 15,000 in PY1; ETB 8,000/yr thereafter (model). |
| Seasonality | Build stock Jul.-Dec.; peak sales Jan.-May (index 1.2-1.6). |
| Collection | Cash/mobile money for walk-in sales; invoices with 30-day terms for institutions; credit limit per dealer. |
| KPIs | Tonnes sold per month vs plan; share to repeat buyers >= 60%; average price >= ETB 16 (PY1 terms); receivables < 30 days; stock age < 3 months. |

## G. Management and governance

The unit should keep separate accounts from the poultry enterprise, even under one group, so each business line's viability stays visible. Internal litter transfer is at handling cost only (ETB 0.1/kg [A]). Roles [A]: production lead (vermicompost), sales lead (shared), treasurer (shared); 1 paid member-worker; poultry duty members check moisture daily (memo value ETB 3,000/month, unpaid). Controls follow the poultry plan: three quotations, stock cards (feedstock in, bags out), two signatories, monthly reconciliation and monthly reporting. Training: vermicomposting practice (HU community service or experienced Sidama producers [V: R9]), quality sampling, bookkeeping by product line.

## H. Financial plan and funding strategy

There is no original vermicompost budget. All figures below are new assumptions at Oct 2026 prices, kept separate from the original poultry budget baseline.

| Investment item [A] | ETB | Timing |
| --- | --- | --- |
| Phase 1 structures (shade, 16 beds, tank and gutters, pre-compost bay) | 110,000 | Month 4 |
| Phase 1 tools (screens, wheelbarrows, forks, scale, thermometer, PPE) | 18,000 | Month 4 |
| Starter earthworms 24 kg x ETB 450 (pre-operating, expensed) | 10,800 | Month 5 |
| Phase 2 structures and tools (PY1 prices; escalated 12% in model) | 85,000 | Month 16 (if gate passed) |
| Total | 223,800 |  |

| Funding (base) [A] | ETB | Status |
| --- | --- | --- |
| Member equity | 20,000 | Members' agreement needed |
| Investment loan, 22%, 6 months grace, 36 instalments | 120,000 | No lender identified |
| Capital grant | 0 | None confirmed - not assumed |
| Additional funding required (model output) | 318,974 | Source not identified |

### Unit economics (PY1 prices, steady state)

| Measure per kg saleable | ETB |
| --- | --- |
| Raw feedstock required (kg) | 5.13 |
| Feedstock cost | 2.56 |
| Casual handling and screening labour | 1.52 |
| Bag and delivery | 2.00 |
| Total variable cost | 6.08 |
| Selling price | 16.00 |
| Contribution | 9.92 (62%) |
| Fixed costs + depreciation + interest, PY3 (ETB/yr) | 196,275 |
| Break-even volume (t/yr) | 19.8 |
| Break-even price at planned PY3 volume | 15.45 |
| Return to members' labour per day worked, PY3 | ETB 350 (vs ETB 250/day casual wage assumption) |

### Five-year summary (base)

| Item | PY1 | PY2 | PY3 | PY4 | PY5 |
| --- | --- | --- | --- | --- | --- |
| Vermicompost sold (t) | 2.5 | 11.7 | 21.0 | 21.2 | 21.2 |
| Sales revenue | 40,213 | 220,892 | 433,840 | 491,663 | 550,663 |
| EBITDA | (77,759) | (24,690) | 78,661 | 93,310 | 104,507 |
| Net profit | (107,161) | (67,570) | 36,509 | 58,581 | 71,845 |
| Net cash from operations | (99,893) | (53,981) | 62,587 | 84,171 | 96,270 |
| Additional funding required | 100,174 | 182,616 | 36,185 | - | - |
| Closing cash | 5,000 | 5,000 | 62,192 | 108,657 | 204,928 |
| Loan outstanding | 112,720 | 79,285 | 37,706 | - | - |
| DSCR | -2.89 | -0.45 | 1.43 | 2.16 | n/a |

| Appraisal | NPV @ 25% | IRR | Payback |
| --- | --- | --- | --- |
| Full investment (base) | (147,559) | 5% | 4.7 yrs |

The loan cannot be serviced from operations in PY1-PY2 (DSCR below 1). This is why the plan recommends equity- or grant-funded piloting. Profit and cash diverge because of capex, worm-stock expensing and a 30% credit share of sales. The full statements are in Annex 4.

## I. Scenarios and risk management

| Indicator | Base | Downside | Upside |
| --- | --- | --- | --- |
| Key assumptions | ETB 16/kg; 22 t demand; feedstock 0.5/kg; 3-month cycle; 85% utilisation; Phase 2 built | ETB 12/kg; 12 t demand; feedstock 1.0/kg; 4-month cycle; 70% utilisation; no Phase 2; 1-month delay | ETB 20/kg; 30 t demand; feedstock 0.3/kg; 90% utilisation |
| Sales PY1-5 | 1,737,271 | 325,587 | 2,684,481 |
| Net profit PY1-5 | (7,795) | (933,364) | 936,931 |
| Additional funding required | 318,974 | 991,509 | 159,313 |
| NPV @ 25% | (147,559) | (514,779) | 306,859 |
| Break-even price (ETB/kg) | 15.4 | 39.7 | 11.9 |

| Factor moved to downside (others base) | Net profit PY1-5 | Extra funding | NPV @ 25% |
| --- | --- | --- | --- |
| Base case | (7,795) | 318,974 | (147,559) |
| Blended ex-site price of vermicompost incl. 25 kg bag | (409,514) | 546,977 | (331,168) |
| Accessible annual demand at full market development | (389,345) | 705,367 | (337,416) |
| Cattle manure / crop residue / coffee pulp, delivered | (248,589) | 442,880 | (263,640) |
| Bed utilisation at steady state (water, downtime, losses) | (157,300) | 341,454 | (212,702) |
| Cycle length incl. harvest and re-bedding | (259,494) | 407,533 | (264,700) |
| Phase 2 expansion goes ahead (1 = yes, 0 = no) | (169,525) | 239,391 | (157,854) |
| Dry-matter loss during vermicomposting | (104,232) | 339,125 | (191,789) |
| Share of sales collected in month of sale | (7,795) | 325,081 | (149,063) |
| Delivery cost | (46,243) | 327,692 | (165,532) |
| Poultry litter available from the pullet enterprise | (12,139) | 320,605 | (149,761) |

### Risk register

| Risk | L | I | Warning indicator | Mitigation | Responsible |
| --- | --- | --- | --- | --- | --- |
| Low demand / slow uptake | H | H | < 50% of monthly sales target for 2 months; stock > 3 months | Pre-season agreements with nurseries; demonstrations; pause bed loading | Sales lead |
| Price pressure from cheap compost and project giveaways | M-H | H | Offers < ETB 14/kg | Differentiate (screened, tested, bagged); target nurseries | Sales lead |
| Feedstock shortage (manure competition, seasonality) | H | H | Contracted supply < 80% of need | Written supply/barter deals; coffee pulp/crop residues; size beds to secured feedstock | Production lead |
| Contamination (plastics, pathogens, veterinary drug residues, disease-culled litter) | M | H | Visible debris; failed lab test | Acceptance criteria; full pre-composting; batch hold until tests | Production lead |
| Worm mortality (ammonia, heat, flooding, predators) | M | H | Worms surfacing/escaping; bed temperature > 35 C | Pre-compost litter; shade; moisture checks; ant/rat barriers; reserve worm bed | Duty members |
| Water interruption in dry season | M | M | Tank < 25% | Roof harvesting; mulch cover; reduce active beds | Worker |
| Production delays (cycle > 3 months) | M | M | Harvest dates slip | Smaller feed layers; more frequent checks | Production lead |
| Transport cost increases | M | M | Delivery cost > ETB 1.2/kg | Ex-site sales; group deliveries | Treasurer |
| Delayed payments by dealers/institutions | M | M | Receivables > 30 days | Credit limits; deposits | Treasurer |
| Regulatory uncertainty (organic fertiliser registration/labels) | M | M | Authority enquiry | Early consultation; modest labels | Chair |

## J. Implementation and monitoring

Additional activities proposed by this plan, NOT part of the original schedule [A]. Month 1 = the original 'Sep.' column; year not stated.

| Months | Activity | Responsible | Budget (ETB) | Milestone / decision |
| --- | --- | --- | --- | --- |
| M1-M2 (Sep.-Oct.) | Buyer survey (nurseries, horticulture, dealers); feedstock mapping and supply agreements; worm supplier identified; lab identified | Sales and production leads; DA | Within equity | Gate V0: >= 5 t/yr letters of intent; >= 60 t/yr feedstock arranged |
| M3-M4 (Nov.-Dec.) | Plot allocation; build Phase 1 (or a 4-6 bed pilot); training | Chair; HU community service (if agreed) | 128,000 (or ~35,000 for 6 beds) | Beds ready |
| M5-M7 (Jan.-Mar.) | Stock worms; pre-compost first litter (from M7); ramp-up | Worker | 10,800 worms | Worm density doubling |
| M8-M12 (Apr.-Aug.) | First harvests; lab test; first sales; demonstrations | Production + sales | Testing 6,000; marketing | Gate V1 (M12): price >= ETB 16; conversion >= 0.2 kg/kg raw; buyers >= 10 t/yr |
| M16-M17 (Dec.-Jan.) PY2 | Phase 2 only if Gate V1 is passed | General assembly | 85,000 + escalation | Expansion |

| Indicator | Frequency | Target |
| --- | --- | --- |
| Raw feedstock received (t) and source | Weekly | Per plan; 100% logged |
| Bed utilisation and cycle length | Monthly | >= 85%; <= 3 months |
| Conversion: saleable kg per kg raw | Per harvest | >= 0.19 (base 0.195) |
| Lab test pass rate | Twice a year | 100% vs internal specification |
| Tonnes sold; average price; repeat buyers | Monthly | Plan; >= ETB 16; >= 60% |
| Contribution margin and cash collected | Monthly | >= 55%; receivables < 30 days |
| Operating cost per kg | Quarterly | <= plan +10% |

## K. Environmental and social performance

Waste diversion (transparent calculation): ~109 t/yr of organic residues processed at full scale, incl. ~8 t of poultry litter that might otherwise be stockpiled or dumped [A].

Water: ~2-4 m3/month for 32 beds [A]; roof harvesting from ~120-240 m2 of roof can supply much of this in rainy months.

Runoff and odour: leachate captured in a lined pit and returned to pre-composting; covered pre-compost heaps; site away from streams and homes.

Worker safety: biological hazards from raw litter (gloves, boots, masks, handwashing); manual-handling limits (25 kg bags).

Employment and inclusion: 1-1.5 paid positions plus casual days for young women members [A]; return to labour ~ETB 350/day in PY3 (base).

Soil benefits: organic matter and nutrient recycling are plausible but not quantified here. No field data for these woredas exists yet.

Carbon credits: not counted; no verified, accessible mechanism exists for a unit of this size.

Regulation: no specific Ethiopian framework for bio-fertilisers was found; draft guidelines and standards have been reported as under development [V: R26, R27]. Confirm with the Ethiopian Agricultural Authority and the regional agriculture bureau whether vermicompost sold as a soil amendment needs registration or labelling approval. Environmental screening under Proc. 1371/2025 [V: R25] is likely low-category - confirm locally.

# 3. Annex - Original Data and Assumptions Register

| ID | Item | Value | Origin and location | Use in this plan | Issue |
| --- | --- | --- | --- | --- | --- |
| O-P7 | Location | Two kebeles in two different woredas; kebeles with electricity | Poultry work plan S.1-2 [O] | Site co-location | Not named [G] |
| O-P9 | Members | 10 young female members per group | Poultry work plan [O] | Possible owners/labour | Consent needed [G] |
| O-P11 | Cost-sharing | Woreda builds house; project supplies inputs | Poultry work plan [O] | Shared site/store | No VC contribution agreed [G] |
| O-P24 | Equipment line | '... brooder box, watering, feeder , saw dust etc' - 30,000 | Poultry budget [O] | Sawdust litter = feedstock | Litter quantity not stated [G] |
| O-P17 | Support | HU community service department training and exchange visits | Poultry work plan S.4 [O] | Possible training partner | Not committed [G] |
| O-P16 | Schedule | Sep.-Aug., no year | Poultry work plan S.3 [O] | Month-1 alignment | Year not stated [G] |
| A-all | All VC quantities, prices, costs and funding | See Annex 4 assumption table | New [A] | Model inputs | Validate before investment |

# 4. Annex - Financial projections (base case, nominal ETB)

## 4.1 PY1 monthly cash flow (Month 1 = original 'Sep.' column; year not stated)

| ETB, PY1 | M1 Sep | M2 Oct | M3 Nov | M4 Dec | M5 Jan | M6 Feb | M7 Mar | M8 Apr | M9 May | M10 Jun | M11 Jul | M12 Aug | PY1 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cash collected | - | - | - | - | - | - | - | 5,824 | 8,320 | 8,320 | 8,245 | 7,392 | 38,101 |
| Variable costs paid | - | - | - | - | (1,733) | (1,733) | (1,467) | (2,897) | (2,897) | (2,897) | (4,097) | (3,950) | (21,670) |
| Fixed costs paid | - | (2,000) | - | (7,750) | (19,563) | (8,763) | (8,763) | (14,763) | (8,763) | (8,763) | (8,763) | (8,763) | (96,657) |
| Interest | - | - | - | (2,200) | (2,200) | (2,200) | (2,200) | (2,200) | (2,200) | (2,200) | (2,156) | (2,112) | (19,668) |
| Net operating cash flow | - | (2,000) | - | (9,950) | (23,497) | (12,697) | (12,430) | (14,036) | (5,540) | (5,540) | (6,771) | (7,433) | (99,893) |
| Cash-funded capex | - | - | - | (128,000) | - | - | - | - | - | - | - | - | (128,000) |
| Member equity | 20,000 | - | - | - | - | - | - | - | - | - | - | - | 20,000 |
| Loan disbursed | - | - | 120,000 | - | - | - | - | - | - | - | - | - | 120,000 |
| Principal repaid | - | - | - | - | - | - | - | - | - | (2,383) | (2,427) | (2,471) | (7,280) |
| Additional funding required (unsourced) | - | - | - | 4,950 | 23,497 | 12,697 | 12,430 | 14,036 | 5,540 | 7,923 | 9,198 | 9,904 | 100,174 |
| Net cash flow | 20,000 | (2,000) | 120,000 | (137,950) | (23,497) | (12,697) | (12,430) | (14,036) | (5,540) | (7,923) | (9,198) | (9,904) | (95,174) |
| Closing cash | 20,000 | 18,000 | 138,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 | 5,000 |  |

## 4.2 Income statement

| ETB (nominal) | PY1 | PY2 | PY3 | PY4 | PY5 | PY1-5 |
| --- | --- | --- | --- | --- | --- | --- |
| Vermicompost sales | 40,213 | 209,132 | 420,669 | 476,911 | 534,141 | 1,681,066 |
| Earthworm sales | - | 11,760 | 13,171 | 14,752 | 16,522 | 56,205 |
| Total sales revenue | 40,213 | 220,892 | 433,840 | 491,663 | 550,663 | 1,737,271 |
| Poultry litter handling | (400) | (896) | (1,004) | (1,124) | (1,259) | (4,682) |
| Other feedstock delivered | (10,533) | (40,021) | (63,222) | (70,808) | (79,305) | (263,890) |
| Casual labour - feedstock | (3,760) | (13,350) | (20,472) | (22,928) | (25,680) | (86,190) |
| Casual labour - harvest/screening | (1,950) | (10,789) | (19,618) | (22,355) | (25,038) | (79,750) |
| Bags and labels | (3,016) | (15,685) | (31,550) | (35,768) | (40,061) | (126,080) |
| Delivery | (2,011) | (10,457) | (21,033) | (23,846) | (26,707) | (84,053) |
| Total variable costs | (21,670) | (91,198) | (156,898) | (176,830) | (198,049) | (644,646) |
| Inventory build-up (reduces cost of sales) | 354 | 5,410 | 140 | 708 | 794 | 7,406 |
| Gross margin | 18,897 | 135,104 | 277,082 | 315,542 | 353,407 | 1,100,032 |
| Paid member-workers | (54,000) | (107,520) | (135,475) | (151,732) | (169,940) | (618,668) |
| Water | (3,840) | (10,752) | (14,451) | (16,185) | (18,127) | (63,354) |
| Laboratory testing | (6,000) | (13,440) | (15,053) | (16,859) | (18,882) | (70,234) |
| Marketing and demonstrations | (11,250) | (8,960) | (10,035) | (11,239) | (12,588) | (54,073) |
| Administration | (4,500) | (6,720) | (7,526) | (8,430) | (9,441) | (36,617) |
| Maintenance | (4,267) | (10,722) | (13,999) | (15,679) | (17,560) | (62,227) |
| Registration and licences | (2,000) | (1,680) | (1,882) | (2,107) | (2,360) | (10,029) |
| Starter earthworms (pre-operating) | (10,800) | - | - | - | - | (10,800) |
| Total fixed operating costs | (96,657) | (159,794) | (198,421) | (222,232) | (248,899) | (926,003) |
| EBITDA excluding grants | (77,759) | (24,690) | 78,661 | 93,310 | 104,507 | 174,029 |
| Depreciation | (9,733) | (21,320) | (24,680) | (24,680) | (24,680) | (105,093) |
| Interest | (19,668) | (21,560) | (13,415) | (3,540) | - | (58,183) |
| Profit before grants and tax | (107,161) | (67,570) | 40,566 | 65,090 | 79,827 | 10,753 |
| Grant income - in-kind inputs (non-cash, one-off) | - | - | - | - | - | - |
| Income tax (placeholder 10%) | - | - | (4,057) | (6,509) | (7,983) | (18,548) |
| NET PROFIT | (107,161) | (67,570) | 36,509 | 58,581 | 71,845 | (7,795) |
| Memo: net profit excluding grant income | (107,161) | (67,570) | 36,509 | 58,581 | 71,845 | (7,795) |
| Memo: imputed unpaid member labour | 27,000 | 40,320 | 45,158 | 50,577 | 56,647 | 219,703 |
| Memo: economic profit after imputed labour, excl. grants | (134,161) | (107,890) | (8,649) | 8,004 | 15,198 | (227,498) |

## 4.3 Cash-flow statement

| ETB (nominal) | PY1 | PY2 | PY3 | PY4 | PY5 | PY1-5 |
| --- | --- | --- | --- | --- | --- | --- |
| Cash collected from customers | 38,101 | 218,571 | 431,321 | 490,829 | 549,728 | 1,728,550 |
| Variable costs paid in cash | (21,670) | (91,198) | (156,898) | (176,830) | (198,049) | (644,646) |
| Fixed costs paid | (96,657) | (159,794) | (198,421) | (222,232) | (248,899) | (926,003) |
| Interest paid | (19,668) | (21,560) | (13,415) | (3,540) | - | (58,183) |
| Income tax paid | - | - | - | (4,057) | (6,509) | (10,566) |
| Net cash from operations | (99,893) | (53,981) | 62,587 | 84,171 | 96,270 | 89,153 |
| Net cash from investing (cash-funded capex) | (128,000) | (95,200) | - | - | - | (223,200) |
| Member equity | 20,000 | - | - | - | - | 20,000 |
| Loan disbursed | 120,000 | - | - | - | - | 120,000 |
| Loan principal repaid | (7,280) | (33,435) | (41,579) | (37,706) | - | (120,000) |
| Additional funding required (source not identified) | 100,174 | 182,616 | 36,185 | - | - | 318,974 |
| Net cash from financing | 232,893 | 149,181 | (5,395) | (37,706) | - | 338,974 |
| Net change in cash | 5,000 | - | 57,192 | 46,465 | 96,270 | 204,928 |
| Closing cash | 5,000 | 5,000 | 62,192 | 108,657 | 204,928 |  |
| Lowest month-end cash in year | 5,000 | 5,000 | 5,000 | 21,412 | 79,159 |  |

## 4.4 Balance sheet

| ETB, end of year | PY1 | PY2 | PY3 | PY4 | PY5 |
| --- | --- | --- | --- | --- | --- |
| Cash | 38,101 | 218,571 | 431,321 | 490,829 | 549,728 |
| Trade receivables | 2,112 | 4,434 | 6,953 | 7,787 | 8,721 |
| Finished-goods inventory | 354 | 5,764 | 5,904 | 6,613 | 7,406 |
| Net fixed assets (incl. in-kind assets) | 118,267 | 192,147 | 167,467 | 142,787 | 118,107 |
| TOTAL ASSETS | 125,733 | 207,344 | 242,516 | 265,843 | 339,162 |
| Loan outstanding | 112,720 | 79,285 | 37,706 | - | - |
| Income tax payable | - | - | 4,057 | 6,509 | 7,983 |
| Total liabilities | 112,720 | 79,285 | 41,762 | 6,509 | 7,983 |
| Member paid-in capital | 20,000 | 20,000 | 20,000 | 20,000 | 20,000 |
| Contributed capital (grants, in-kind assets) | - | - | - | - | - |
| Additional funding required, cumulative (unsourced) | 100,174 | 282,790 | 318,974 | 318,974 | 318,974 |
| Retained earnings | (107,161) | (174,730) | (138,221) | (79,640) | (7,795) |
| Total equity | 13,013 | 128,059 | 200,753 | 259,334 | 331,179 |
| TOTAL LIABILITIES AND EQUITY | 125,733 | 207,344 | 242,516 | 265,843 | 339,162 |
| Check (assets - liabilities - equity) | - | - | - | - | - |

## 4.5 Production statistics (kg, fresh weight)

| kg | PY1 | PY2 | PY3 | PY4 | PY5 |
| --- | --- | --- | --- | --- | --- |
| Raw feedstock collected | 25,067 | 79,467 | 108,800 | 108,800 | 108,800 |
| of which poultry litter | 4,000 | 8,000 | 8,000 | 8,000 | 8,000 |
| of which other feedstock | 21,067 | 71,467 | 100,800 | 100,800 | 100,800 |
| Bed feed loaded | 18,800 | 59,600 | 81,600 | 81,600 | 81,600 |
| Unscreened vermicompost harvested | 3,250 | 16,055 | 26,065 | 26,520 | 26,520 |
| Saleable vermicompost produced | 2,600 | 12,844 | 20,852 | 21,216 | 21,216 |
| Vermicompost sold | 2,513 | 11,670 | 20,960 | 21,216 | 21,216 |
| Demand reachable | 8,800 | 15,400 | 22,000 | 22,000 | 22,000 |
| Closing inventory (kg) | 87 | 1,260 | 1,153 | 1,153 | 1,153 |

## 4.6 Assumptions (Base / Downside / Upside)

| Assumption | Unit | Base | Downside | Upside | Status / source / note |
| --- | --- | --- | --- | --- | --- |
| 1. Timing (model month 1 = 'Sep.' month of the original poultry schedule; year not stated in source) |  |  |  |  |  |
| Phase 1 construction complete | month | 4 | 5 | 4 | NEW ASSUMPTION (not in original proposal). Aligned with poultry house construction. |
| Earthworms stocked / operations start | month | 5 | 6 | 5 | NEW ASSUMPTION (not in original proposal). |
| Phase 2 expansion goes ahead (1 = yes, 0 = no) | switch | 1 | - | 1 | NEW ASSUMPTION (not in original proposal). Decision gate at end of PY1 (see business plan). Downside assumes the gate is not passed. |
| Phase 2 beds operational | month | 17 | 17 | 15 | NEW ASSUMPTION (not in original proposal). Base: PY2 month 5 (Jan.). |
| 2. Production system and material flow |  |  |  |  |  |
| Phase 1 vermibeds (1 m x 3 m x 0.5 m, lined ground beds under shade) | beds | 16 | 16 | 16 | NEW ASSUMPTION (not in original proposal). |
| Phase 2 additional vermibeds | beds | 16 | 16 | 16 | NEW ASSUMPTION (not in original proposal). |
| Pre-composted feed loaded per bed per cycle (fresh weight) | kg | 750 | 700 | 800 | NEW ASSUMPTION (not in original proposal). ~1.5 m3 working volume x ~0.5 t/m3, fed in layers during the cycle. VERIFY |
| Cycle length incl. harvest and re-bedding | months | 3 | 4 | 3 | NEW ASSUMPTION (not in original proposal). E. fetida processes pre-composted manure in ~45-90 days at 15-35 C and 60-70% moisture (ISFM+ guidance; ASTU thesis used 45 days). |
| Ramp-up period after stocking (worm multiplication) | months | 6 | 6 | 6 | NEW ASSUMPTION (not in original proposal). |
| Bed utilisation during ramp-up | % | 50.0% | 40.0% | 50.0% | NEW ASSUMPTION (not in original proposal). |
| Bed utilisation at steady state (water, downtime, losses) | % | 85.0% | 70.0% | 90.0% | NEW ASSUMPTION (not in original proposal). |
| Mass loss during 2-4 week pre-composting (fresh basis) | % of raw | 25.0% | 30.0% | 22.0% | NEW ASSUMPTION (not in original proposal). Pre-composting is required for poultry litter (ammonia/salts kill worms; Oklahoma State thesis; 2025 Belarus study). |
| Dry matter of bed feed | % | 30.0% | 30.0% | 30.0% | NEW ASSUMPTION (not in original proposal). VERIFY |
| Dry-matter loss during vermicomposting | % of DM | 35.0% | 40.0% | 33.0% | NEW ASSUMPTION (not in original proposal). Typical 30-45% organic-matter mineralisation. VERIFY |
| Moisture of product at sale | % | 40.0% | 40.0% | 40.0% | NEW ASSUMPTION (not in original proposal). Declare on label; sell by weight at stated moisture. |
| Screening oversize / rejects (returned to beds, not sold) | % of harvest | 10.0% | 15.0% | 8.0% | NEW ASSUMPTION (not in original proposal). |
| Material retained as worm bedding / inoculum | % of harvest | 10.0% | 10.0% | 10.0% | NEW ASSUMPTION (not in original proposal). |
| Unscreened vermicompost per kg bed feed (computed) | kg/kg | computed |  | 0.33 | Dry-matter balance: feed DM x (1 - DM loss) / (1 - product moisture). |
| Raw feedstock needed per kg SALEABLE product (computed) | kg/kg | computed |  | 5.13 | Formula. |
| 3. Feedstock |  |  |  |  |  |
| Poultry litter available from the pullet enterprise | t/yr | 8 | 6 | 8 | NEW ASSUMPTION (not in original proposal). ~2 t per 500-bird batch x 4 batches (droppings + sawdust). Depends on poultry enterprise operating. VERIFY |
| First month litter is available | month | 7 | 8 | 7 | NEW ASSUMPTION (not in original proposal). After first poultry batch. |
| Poultry litter cost (internal; handling only) | ETB/kg | 0.10 | 0.20 | 0.10 | NEW ASSUMPTION (not in original proposal). |
| Cattle manure / crop residue / coffee pulp, delivered | ETB/kg | 0.50 | 1 | 0.30 | NEW ASSUMPTION (not in original proposal). Often free at source; cost is mainly cart transport. Competes with farmers' own use. VERIFY |
| 4. Market and prices (PY1 prices; escalated annually) |  |  |  |  |  |
| Accessible annual demand at full market development | t/yr | 22 | 12 | 30 | NEW ASSUMPTION (not in original proposal). Hypothesis built up in plan section C (nurseries, horticulture, smallholder adopters). Must be validated by interviews and pilot sales. |
| Market development: share of demand reachable in PY1 | % | 40.0% | 30.0% | 50.0% | NEW ASSUMPTION (not in original proposal). |
| Market development: share of demand reachable in PY2 | % | 70.0% | 60.0% | 80.0% | NEW ASSUMPTION (not in original proposal). |
| Blended ex-site price of vermicompost incl. 25 kg bag | ETB/kg | 16 | 12 | 20 | NEW ASSUMPTION (not in original proposal). CGIAR/IWMI (Rift Valley, Oct 2025): ETB 1,000/qt to households; ETB 1,600/qt to collectors. Base blends bulk ~13 and bagged ~19. VERIFY |
| Surplus earthworms sold (from PY2) | kg/yr | 30 | 10 | 60 | NEW ASSUMPTION (not in original proposal). Thin market, mainly projects/NGOs. |
| Earthworm price | ETB/kg | 350 | 300 | 400 | NEW ASSUMPTION (not in original proposal). CGIAR/IWMI 2025: ETB 300-500/kg producer; 600-800 collectors' resale. |
| Share of sales collected in month of sale | % | 70.0% | 50.0% | 80.0% | NEW ASSUMPTION (not in original proposal). |
| Annual price escalation | %/yr | 12.0% | 8.0% | 12.0% | NEW ASSUMPTION (not in original proposal). CPI 15.3% (Jul 2026). |
| Annual cost escalation | %/yr | 12.0% | 15.0% | 12.0% | NEW ASSUMPTION (not in original proposal). |
| Demand seasonality index - Sep | index | 0.60 | 0.60 | 0.60 | NEW ASSUMPTION (not in original proposal). Peaks before belg and kiremt planting and nursery potting (Jan.-May). Average = 1.0. VERIFY |
| Demand seasonality index - Oct | index | 0.60 | 0.60 | 0.60 |  |
| Demand seasonality index - Nov | index | 0.70 | 0.70 | 0.70 |  |
| Demand seasonality index - Dec | index | 0.80 | 0.80 | 0.80 |  |
| Demand seasonality index - Jan | index | 1.20 | 1.20 | 1.20 |  |
| Demand seasonality index - Feb | index | 1.50 | 1.50 | 1.50 |  |
| Demand seasonality index - Mar | index | 1.60 | 1.60 | 1.60 |  |
| Demand seasonality index - Apr | index | 1.40 | 1.40 | 1.40 |  |
| Demand seasonality index - May | index | 1.30 | 1.30 | 1.30 |  |
| Demand seasonality index - Jun | index | 1 | 1 | 1 |  |
| Demand seasonality index - Jul | index | 0.70 | 0.70 | 0.70 |  |
| Demand seasonality index - Aug | index | 0.60 | 0.60 | 0.60 |  |
| 5. Variable costs |  |  |  |  |  |
| Bag size | kg | 25 | 25 | 25 | NEW ASSUMPTION (not in original proposal). |
| Woven bag + printed label | ETB/bag | 30 | 35 | 28 | NEW ASSUMPTION (not in original proposal). VERIFY |
| Casual labour: harvest and screening | ETB/kg harvested | 0.60 | 0.80 | 0.50 | NEW ASSUMPTION (not in original proposal). ~ETB 250/day casual rate. VERIFY |
| Casual labour: feedstock handling and turning | ETB/kg raw | 0.15 | 0.20 | 0.12 | NEW ASSUMPTION (not in original proposal). |
| Delivery cost | ETB/kg sold | 0.80 | 1.20 | 0.70 | NEW ASSUMPTION (not in original proposal). VERIFY |
| 6. Fixed costs (PY1 prices) |  |  |  |  |  |
| Paid member-workers, Phase 1 | FTE | 1 | 1 | 1 | NEW ASSUMPTION (not in original proposal). Supervision shared with poultry duty members (integration benefit). |
| Additional paid workers, Phase 2 | FTE | 0.50 | 0.50 | 0.50 | NEW ASSUMPTION (not in original proposal). |
| Monthly pay per FTE | ETB/month | 6,000 | 6,000 | 6,000 | NEW ASSUMPTION (not in original proposal). ~ETB 250/day x 24 days. VERIFY |
| Imputed unpaid member supervision (memo only) | ETB/month | 3,000 | 3,000 | 3,000 | NEW ASSUMPTION (not in original proposal). |
| Water per active bed | ETB/bed/month | 30 | 50 | 25 | NEW ASSUMPTION (not in original proposal). Rain-water harvesting reduces this. VERIFY |
| Laboratory test per batch sample (twice a year) | ETB/test | 6,000 | 8,000 | 6,000 | NEW ASSUMPTION (not in original proposal). Nutrients, pH, EC, C:N, maturity, pathogens (E. coli/Salmonella). Lab to be identified. VERIFY |
| Marketing and demonstrations, PY1 | ETB/yr | 15,000 | 15,000 | 15,000 | NEW ASSUMPTION (not in original proposal). |
| Marketing and demonstrations, PY2 onward | ETB/yr | 8,000 | 8,000 | 8,000 | NEW ASSUMPTION (not in original proposal). |
| Administration | ETB/month | 500 | 500 | 500 | NEW ASSUMPTION (not in original proposal). |
| Maintenance | % of cumulative capex/yr | 5.0% | 5.0% | 5.0% | NEW ASSUMPTION (not in original proposal). |
| Registration of activity / licence amendment (one-off) | ETB | 2,000 | 2,000 | 2,000 | NEW ASSUMPTION (not in original proposal). VERIFY |
| Annual licence renewal | ETB/yr | 1,500 | 1,500 | 1,500 | NEW ASSUMPTION (not in original proposal). VERIFY |
| Starter earthworms purchased (E. fetida) | kg | 24 | 24 | 24 | NEW ASSUMPTION (not in original proposal). ~0.5 kg/m2 on 48 m2, multiplied during ramp-up. |
| Purchase price of starter worms | ETB/kg | 450 | 500 | 400 | NEW ASSUMPTION (not in original proposal). CGIAR/IWMI 2025 range. VERIFY |
| 7. Investment |  |  |  |  |  |
| Phase 1 structures: shade (~120 m2), 16 lined ground beds, 1 m3 tank + gutters, pre-compost bay (store shared with poultry) | ETB | 110,000 | 125,000 | 100,000 | NEW ASSUMPTION (not in original proposal). Low-cost design: eucalyptus poles, corrugated iron roof (~70k), plastic-lined ground beds with drainage (~1,500 each), rain-water tank. Obtain 3 quotations. VERIFY |
| Phase 1 tools: screens, wheelbarrows, forks, scale, thermometer, moisture meter, PPE | ETB | 18,000 | 20,000 | 18,000 | NEW ASSUMPTION (not in original proposal). VERIFY |
| Phase 2 structures: shade + 16 beds | ETB | 80,000 | 90,000 | 75,000 | NEW ASSUMPTION (not in original proposal). VERIFY |
| Phase 2 tools | ETB | 5,000 | 6,000 | 5,000 | NEW ASSUMPTION (not in original proposal). |
| Capital grant for Phase 1 (none confirmed) | ETB | - | - | - | NEW ASSUMPTION (not in original proposal). No partner commitment exists. Set >0 only when confirmed in writing. |
| Useful life - structures | years | 10 | 10 | 10 | NEW ASSUMPTION (not in original proposal). |
| Useful life - tools | years | 5 | 5 | 5 | NEW ASSUMPTION (not in original proposal). |
| 8. Financing, tax and appraisal |  |  |  |  |  |
| Month member equity is paid in | month | 1 | 1 | 1 | NEW ASSUMPTION (not in original proposal). |
| Minimum cash buffer to maintain | ETB | 5,000 | 5,000 | 5,000 | Assumption; any shortfall below this is shown as additional funding required. |
| Member cash equity | ETB | 20,000 | 20,000 | 20,000 | NEW ASSUMPTION (not in original proposal). VERIFY |
| Loan disbursement month | month | 3 | 3 | 3 | NEW ASSUMPTION (not in original proposal). |
| Investment loan | ETB | 120,000 | 120,000 | 120,000 | NEW ASSUMPTION (not in original proposal). No lender identified. |
| Interest rate | %/yr | 22.0% | 26.0% | 20.0% | NEW ASSUMPTION (not in original proposal). NBE policy rate 16% from 13 Jul 2026. VERIFY |
| Grace period (interest only) | months | 6 | 6 | 6 | NEW ASSUMPTION (not in original proposal). |
| Repayment period after grace | months | 36 | 36 | 36 | NEW ASSUMPTION (not in original proposal). |
| Monthly instalment (computed) | ETB/month | computed |  | 4,583 | Formula. |
| Business income tax provision | % of PBT | 10.0% | 10.0% | 10.0% | PLACEHOLDER - verify (see poultry model note). |
| Discount rate (nominal) | % | 25.0% | 25.0% | 25.0% | As poultry model. |
| Standard variable cost per kg saleable (for inventory valuation) | ETB/kg | computed |  | 4.08 | Formula (PY1 prices). |

# 5. Annex - Current-market comparison

There are no original vermicompost figures to compare. The table contrasts the plan's assumptions with the current evidence found.

| Parameter | Plan assumption [A] | Current evidence | Difference / implication |
| --- | --- | --- | --- |
| Vermicompost price | ETB 16/kg blended | ETB 10/kg household; ETB 16/kg via collectors, Oct 2025 [V: R8] | Base sits at the collector price; with ~15% inflation it is plausible but untested; break-even ETB 15.4 |
| Earthworm price | Buy ETB 450; sell ETB 350/kg | ETB 300-500/kg producer; 600-800 resale [V: R8] | Within range |
| Production cost | Variable ETB ~6/kg + fixed | ETB 2.13/kg research estimate [R38] | Research cost excludes marketing, bags, paid labour |
| Business model viability | Thin in base | Research-supported, wet-season, modern systems BCR 1.8-2.2; traditional, dry-season, co-op-led BCR < 1 [V: R8] | Consistent: viability depends on model choice |
| Interest rate | 22% | NBE policy rate 16% (Jul 2026) [V: R3] | Debt is expensive for a slow-ramp business |
| Inflation | 12%/yr escalation | CPI 15.3% (Jul 2026) [V: R2] | Costs may outpace prices (downside) |

# 6. Annex - Prioritised missing information and validation tasks

| # | Task | Why |
| --- | --- | --- |
| 1 | Members' decision to take on vermicompost; separate accounts | Ownership and labour |
| 2 | Buyer survey of all nurseries/horticulture within 30 km; letters of intent | Demand and price |
| 3 | Feedstock inventory and written supply/barter agreements (manure, residues, coffee pulp) | Critical constraint |
| 4 | Weigh actual poultry litter per batch | Feedstock planning |
| 5 | Quotations: shade materials, liners, tank, tools, bags; verified E. fetida supplier | Capex accuracy |
| 6 | Identify an accredited lab and the test price | Quality assurance |
| 7 | Regulatory confirmation for sale/labelling of vermicompost | Compliance |
| 8 | Run a 4-6 bed pilot for 2 cycles; measure conversion, labour hours, losses | Replace technical assumptions |
| 9 | Obtain the full CGIAR/IWMI (R8) and TechnoServe (R9) reports | Benchmark costs and prices |
| 10 | Identify grant or concessional funding for the pilot (none confirmed) | Funding gap |

# 7. Annex - References (accessed 22-23 Oct 2026)

| Ref | Source | Date | Link | Use / caveat |
| --- | --- | --- | --- | --- |
| R1 | Original proposal: 'BENEFIT REALISE Project HwU Cluster Work plan on Integrated Strategies for Resilience - Theme: Livestock - Small-scale poultry enterprises ...' (file HwU_Cluster_work_plan_for_pilot_study.docx) | Undated (project period stated as 2018-2020) | Supplied by the user | Sole source of [O] data. |
| R2 | Capital Ethiopia, 'Ethiopia's growth paradox ...' (annual inflation 15.3% in July 2026; food 15.7%; non-food 14.8%) | 6 Sep 2026 | https://capitalethiopia.com/2026/09/06/ethiopias-growth-paradox-is-the-fastest-growing-economy-in-africa-also-its-most-fragile/ | Inflation; cites Ethiopian Statistical Service. |
| R3 | Ecofin Agency, 'Ethiopia drops bank lending caps, raises rates to keep inflation in check' (NBE policy rate 15% to 16%, 13 Jul 2026) | Jul 2026 | https://www.ecofinagency.com/news-finances/1407-57359-ethiopia-drops-bank-lending-caps-raises-rates-to-keep-inflation-in-check | Financing cost. |
| R4 | Trading Economics, 'Ethiopia Lifts Key Policy Rate to 16%' | Jul 2026 | https://tradingeconomics.com/ethiopia/interest-rate/news/566412 | Corroborates R3. |
| R6 | Trading Economics, Ethiopian birr quote (about 163.9 ETB/USD on 22 Oct 2026; down ~20% over 12 months) | 22 Oct 2026 | https://tradingeconomics.com/ethiopia/currency | Exchange rate. Not an NBE official rate. |
| R7 | Dashen Bank, daily exchange rates (USD buying 160.5377 / selling 163.7485 birr) | 5 Sep 2026 | https://dashenbanksc.com/daily-exchange-rates/ | Commercial-bank rate. |
| R8 | Mekuria, W. et al., 'Technical Report: Feasibility of Vermicompost Production' (IWMI / CGIAR Scaling for Impact; Wondo Genet, Misraq Mesqan, Wera and Atote Ulo districts) | Dec 2025 | https://cgspace.cgiar.org/server/api/core/bitstreams/cbef4cc7-ee6a-412a-b32b-0f8712dfbeed/content | Vermicompost prices (ETB 1,000/qt household; ETB 1,600/qt collector), worm prices (ETB 300-500/kg), BCRs. Full text could NOT be opened from this environment (host blocked); figures taken from search-indexed text - verify against the PDF. |
| R9 | TechnoServe (SERES project), 'Vermicompost fact sheet' - 21 producers in Dale and Shebedino, Sidama | Aug 2024 | https://www.technoserve.org/wp-content/uploads/2024/08/TechnoServe-SERES-Vermicompost-Fact-Sheet.pdf | Producer experience; positive ROI reported. Full text not opened (host blocked). |
| R22 | EY Tax News, 'Ethiopia introduces new VAT Proclamation' (Proc. No. 1341/2024; registration threshold ETB 2,000,000; standard rate 15%) | 16 Sep 2024 | https://taxnews.ey.com/news/2024-1698-ethiopia-introduces-new-vat-proclamation-introducing-raft-of-changes | VAT. |
| R23 | Capital Ethiopia - report on amended Commercial Registration and Business Licensing Proclamation (online registration; lease proof dropped) | Oct 2025 | https://capitalethiopia.com/?p=24588 | Proclamation number of the amendment not confirmed. Base law Proc. 980/2016, amended by Proc. 1150/2019. |
| R25 | Environmental and Social Impact Assessment Proclamation No. 1371/2025 (UNEP LEAP record) | 2025 | https://leap.unep.org/en/countries/et/national-legislation/environmental-and-social-impact-assessment-proclamation-no | Screening categories set by directive; replaces Proc. 299/2002. |
| R26 | New Markets Lab, 'A Legal Guide to Strengthen the Ethiopian Fertilizer Market' (no specific framework for bio-fertilizers) | Undated (c. 2019-2021) | https://www.newmarketslab.org/assets/legal_guide/16.pdf | Organic fertiliser regulatory gap. |
| R27 | AFAP, 'A Review of National Fertilizer Regulatory Authorities in Ethiopia' | May 2023 | https://afap-partnership.org/content/uploads/2023/05/Final-Regulatory-Report-Ethiopia.pdf | Fertiliser regulators. |
| R28 | PANORAMA / GIZ ISFM+, 'One quick-win technology for farmers to improve soil fertility - vermiculture and worm compost in Ethiopia' (Eisenia fetida; 60-70% moisture; 15-35 C) | Undated | https://panorama.solutions/en/solution/one-quick-win-technology-farmers-improve-soil-fertility-vermiculture-and-worm-compost | Technical parameters. |
| R29 | 'Vermicomposting of Poultry Litter Using Eisenia foetida' (Oklahoma State University thesis; pre-composting needed) | Undated | https://shareok.org/handle/11244/7947 | Feedstock preparation. |
| R30 | Chicken manure co-composted with straw and peat before vermicomposting with E. foetida (Proc. Natl. Acad. Sci. Belarus, Agrarian series) | 2025 | https://priroda.belnauka.by/jour/article/download/230/193 | Pre-composting reduces worm mortality. |
| R31 | Global Living Wage Coalition, 'Living income report for rural Sidama, Ethiopia' (update) | Sep 2025 | https://www.globallivingwage.org/living-wage-benchmarks/living-income-report-for-rural-sidama-ethiopia/ | Income benchmark (definitions to be read in full). |
| R32 | Kana TV, 'Ethiopia's development bank to offer cheap loans to women and war-affected regions' | Jun 2026 | https://kanatelevision.com/news/ethiopia-s-development-bank-to-offer-cheap-loans-to-women-and-war-affected-regions-that-normally/ | Possible concessional credit line. |
| R38 | Maize productivity and profitability response to inorganic N-P, biochar and vermicompost in acidic soils of NW Ethiopia (PMC12973914) - vermicompost production cost ETB 2,130.29 per t | c. 2025-26 (online) | https://pmc.ncbi.nlm.nih.gov/articles/PMC12973914/ | Production-cost benchmark, not a market price. |
| R39 | 2SCALE, 'Vermicompost multiplication: a game-changer ... Ethiopian agribusiness sector' (vermicompost at USD 17 per 100 kg) | Undated | https://www.2scale.org/en/updates/vermicompost-multiplication-a-game-changer-towards-unleashing-prosperity-and-sustainability-of-the-ethiopian-agribusiness-sector-en | Year and exchange rate not stated. |

Laws referred to but not retrieved (verify):

Labour Proclamation No. 1156/2019 (employment terms, occupational safety and health) - text not retrieved in this research session.

Cooperative Societies Proclamation No. 985/2016 (legal form for youth groups registered through the woreda cooperative office) - text not retrieved.

Commercial Registration and Business Licensing Proclamation No. 980/2016 as amended by Proc. No. 1150/2019 and a later amendment reported in Oct 2025 (R23).

Solid Waste Management Proclamation No. 513/2007 and Environmental Pollution Control Proclamation No. 300/2002 - text not retrieved; check current status.

Fertilizer manufacturing and trade instrument No. 137 (cited as Proclamation No. 137/1998 in one source and as Council of Ministers Regulation No. 137/2007 elsewhere) - number, status and applicability to compost to be verified.

Research limitations: the CGIAR/IWMI and TechnoServe reports could not be opened from the research environment. Their figures come from search-indexed text and must be checked against the originals. No local quotations, buyer commitments or laboratory results exist.